Student’s Guide to Research Projects, Theses and Dissertations

Digital Companion Workbook — Version 1.2.0

Associated book authors: Antonio Clim and Martino Aldrigo

Digital Companion creator and curator: Antonio Clim

PUBLIC RELEASE — DOCUMENTATION CC BY 4.0; CODE MIT

Minimum and full records, gate criteria, route kits and synthetic worked examples for projects, bachelor’s theses and master’s dissertations

This workbook supplies authorial pedagogical controls. It does not replace current regulations, official forms, supervisor decisions, ethics approval, data-owner authority or publisher requirements.

Source book master: v3.9.0 | SHA-256 14eff00a111e9e985cc86e5e640cd9ae967f2e170e7d0768e765f80aa1c092d5

The workbook is licensed under CC BY 4.0. No ISBN, CIP, imprint, publisher endorsement or Zenodo DOI is asserted.

Digital Companion v1.2.0 | 24 August 2026

How to use this companion

Use the smallest record that can support the current decision. Escalate to a full record only when the minimum form cannot preserve the evidence, authority, uncertainty, rights, privacy, complexity or return route required for review.

Authority lock — Current regulations, programme instructions, official forms and named competent authorities prevail. Gate labels, SCOPE, CORPUS, DECIDE and TRACE are authorial pedagogical controls, not official ASE categories or universally validated methods.

Minimum viable operating rule

• Name the assessed product, dominant route, current gate and exact decision question.

• Identify the single missing evidence or authority object that most constrains the decision.

• Complete one minimum record, preserve its version and obtain a reviewable disposition.

• Escalate to the full record only when the risk or audit burden justifies it.

• Return to the earliest responsible gate when new evidence invalidates an earlier commitment.

• Keep sensitive evidence in the authorised workspace and record only safe identifiers or locators.

• Do not leave completed-record cells blank; use “not applicable — reason” where a declared conditional field does not apply.

Record lifecycle

| State | Meaning |
| --- | --- |
| draft | Incomplete working object. |
| candidate | Produced but not yet inspected. |
| reviewed | Assessed by a named reviewer. |
| accepted locally | Admitted for the declared downstream use within the recorded boundary. |
| superseded | Replaced by a named version and retained for provenance. |
| withdrawn | Known to be unusable or unsafe and not to be used. |

The nine-control evidence-to-defence chain

The chain is ordered but reversible. Passing authorises only the next controlled activity. A later defect reopens the earliest gate responsible for the invalid commitment.

| No. | Control or gate | Decision question | Minimum records |
| --- | --- | --- | --- |
| 1 | Project Start Pack / opening control | Is the assessed product, provisional route, access boundary and first decision sufficiently explicit to begin? | ROUTE_SELECTOR_MIN.csv; PROJECT_START_PACK_MIN.csv |
| 2 | Problem Gate | Is the problem specific, consequential, feasible and answerable? | SCOPE_CANVAS_MIN.csv; FEASIBILITY_SPRINT_RECORD_MIN.csv |
| 3 | Evidence Gate | Is the evidence base sufficient, source-verified and fit for the intended decisions? | CORPUS_LEDGER_MIN.csv; CLAIM_EVIDENCE_MAP_MIN.csv |
| 4 | Design Gate | Can the approved plan produce evidence for the question under the relevant authority boundaries? | DECIDE_RECORD_MIN.csv |
| 5 | Execution Gate | Was the approved plan executed in an inspectable, controlled and reconstructable way? | VERSION_MANIFEST_RECORD_MIN.csv; GATE_RECORD_MIN.csv |
| 6 | Claim Gate | What can the evidence support and where must the claim stop? | CLAIM_EVIDENCE_MAP_MIN.csv |
| 7 | Argument Gate | Does the manuscript contain one reconstructible argument rather than a chronology? | CLAIM_EVIDENCE_MAP_MIN.csv |
| 8 | Editorial Gate | Do all semantic, bibliographic, technical and rendered layers preserve the same bounded study? | VERSION_MANIFEST_RECORD_MIN.csv; GATE_RECORD_MIN.csv |
| 9 | Defence Readiness Gate | Do the submitted record, demonstration, slides and oral account describe the same contribution? | DEMONSTRATION_RUNBOOK_MIN.csv; DEFENCE_QUESTION_MATRIX_MIN.csv; GATE_RECORD_MIN.csv |

Gate outcomes

| Outcome | Meaning |
| --- | --- |
| pass | The named evidence supports progression without an unresolved blocking condition. |
| pass with conditions | Progression is authorised only with named conditions, owners and reopening triggers. |
| repair | The current record remains at the same gate pending proportionate correction. |
| return | An earlier gate must be reopened because the defect invalidates a prior commitment. |
| await authority | A named competent authority must resolve the issue before progression. |
| stop | The current route or project is halted and the reason is preserved. |

The eight inquiry routes

A route is selected through its evidence obligation and prohibited inference, not through a fashionable technology label. The common gates remain the same, but the evidence body and valid claim differ by route.

| Code | Route | Dominant question | Minimum planning evidence | Claim still forbidden |
| --- | --- | --- | --- | --- |
| CREATE | Build-and-evaluate | Can a designed artefact address a bounded problem? | Requirements, rationale, accepted tests and evaluation criteria. | Local demonstration becomes production or institutional readiness |
| MODEL | Algorithmic or simulation study | How does a method or system behave under declared conditions? | Formal assumptions, scenarios, comparator and sensitivity analysis. | One dataset, parameter setting or machine becomes universal superiority or model truth |
| PREDICT | Predictive or machine-learning study | How well does a model predict under a locked validation protocol? | Provenance, split logic, baseline, metrics and error analysis. | Best metric becomes universal superiority, fairness or deployment value |
| MEASURE | Quantitative empirical study | What distribution, association or effect is supported by observed data? | Constructs, sampling, protocol, uncertainty and validity threats. | Threshold crossing becomes importance, causality or generalisability |
| INTERPRET | Qualitative inquiry | How do participants experience or make sense of a phenomenon? | Sampling rationale, protocol, reflexive analysis and traceable interpretation. | Recurring theme becomes population prevalence or universal truth |
| EXPLAIN IN CONTEXT | Case study | How and why does a bounded phenomenon unfold in context? | Case boundary, multiple evidence sources and a chain of evidence. | One bounded case becomes general prevalence or universal mechanism |
| SYNTHESISE | Formal evidence synthesis | What does a documented corpus support? | Protocol, reproducible search, study identity, appraisal and synthesis. | Number of favourable publications becomes consensus or universal effectiveness |
| INTEGRATE | Hybrid route | Why must two routes answer one joint question together? | Dominant logic, integration point, adequate resources and both evidence contracts. | More methods become automatic mutual validation |

Route-kit use

• Use one dominant route and name secondary components only when they produce distinct evidence.

• A hybrid route requires an explicit integration product; parallel mini-projects are not integration.

• Open the relevant ROUTE_GATE_PLAN.csv before choosing templates or drafting a claim.

• Treat every worked example as synthetic teaching material, never as empirical evidence or a ready-made thesis result.

Record catalogue

The catalogue links each record to a gate, stage, route scope, full/minimum counterpart, completion test and book anchor. The CSV catalogue remains the machine-readable authority.

| No. | Layer | Record | Gate | Purpose |
| --- | --- | --- | --- | --- |
| 1 | minimum | Claim-Evidence Map - Minimum | Claim / Argument Gate | Make the exact wording, evidence, uncertainty, boundary and counter-evidence inspectable. |
| 2 | minimum | CORPUS Ledger - Minimum | Evidence Gate | Resolve source identity and preserve the reason for inclusion, exclusion and use. |
| 3 | minimum | DECIDE Record - Minimum | Design Gate | Make one consequential decision conditional, evidence-linked and reopenable. |
| 4 | minimum | Defence Question Matrix - Minimum | Defence Readiness Gate | Prepare direct, evidence-anchored and bounded answers, including legitimate uncertainty. |
| 5 | minimum | Demonstration Runbook - Minimum | Defence Readiness Gate | Prepare a route-appropriate evidential demonstration with a safe fallback. |
| 6 | minimum | Feasibility Sprint Record - Minimum | Problem Gate | Test the most expensive uncertainty before full commitment. |
| 7 | minimum | Gate Record - Minimum | Current gate | Record the decision, evidence status, strongest objection and return route for one gate. |
| 8 | minimum | Project Start Pack - Minimum | Project Start Pack | Establish project identity, access, authority and the first reviewable product. |
| 9 | minimum | Route Selector - Minimum | Project Start Pack | Select the dominant route and expose the immediate evidence obligation. |
| 10 | minimum | SCOPE Canvas - Minimum | Problem Gate | Turn an attractive topic into a bounded, answerable and revisable problem. |
| 11 | minimum | TRACE Record - Minimum | All gates | Record consequential generative-AI assistance and its verification and disposition. |
| 12 | minimum | Version and Manifest Record - Minimum | All closure gates | Preserve one source of truth and identify every derivative. |
| 13 | full | Accessibility and Render Audit - Full | Editorial Gate | Preserve structural accessibility and inspect the rendered object page by page. |
| 14 | full | Appraisal Record - Full | Evidence Gate | Separate relevance, authority, methodological quality and fitness for a particular claim. |
| 15 | full | Argument Spine Map - Full | Argument Gate | Transform gate records into one bounded answer rather than a chronology. |
| 16 | full | Authoritative File and Version Record - Full | Editorial Gate | Designate one source of truth and preserve derivative identity. |
| 17 | full | Authority Matrix - Full | Design Gate | Separate advice, academic approval, ethics, data ownership, security and licence authority. |
| 18 | full | Author Identity and Headline Consistency Record - Full | Editorial Gate | Lock author order and headline layers to one study identity. |
| 19 | full | Candidate Artefact and Inspection Record - Full | Execution Gate | Inspect the primary artefact rather than a summary or dashboard. |
| 20 | full | Claim-Evidence Map - Full | Claim / Argument Gate | Map each exact claim to evidence, reasoning, uncertainty, boundary and rejected stronger wording. |
| 21 | full | Core Source Note - Full | Evidence Gate | Record what a load-bearing source actually supports and where its scope ends. |
| 22 | full | CORPUS Ledger - Full | Evidence Gate | Resolve each candidate object from discovery record to claim-linked use. |
| 23 | full | Current Session Authority Record — Full | Defence Readiness Gate | Separate dated official sources, operational values, conflicts, clarifications and recheck dates for the current route and session. |
| 24 | full | DECIDE Record - Full | Design Gate | Record a consequential decision as a conditional commitment. |
| 25 | full | Defence Question Matrix - Full | Defence Readiness Gate | Prepare evidence-return answers to realistic hostile questions. |
| 26 | full | Defence Readiness Record - Full | Defence Readiness Gate | Record whether the scientific record, submitted package, demonstration, slides and oral account preserve one contribution. |
| 27 | full | Demonstration Runbook - Full | Defence Readiness Gate | Prepare a route-specific evidential demonstration, failure case and fallback. |
| 28 | full | Early Test Record - Full | Design Gate | Test one consequential design commitment before full execution. |
| 29 | full | Editorial Revision Map — Full | Editorial Gate | Control meaning-changing and technically consequential edits by location, scale, authority, return gate and retest. |
| 30 | full | Evaluation Design Record - Full | Claim Gate | Design evaluation backwards from the minimum meaningful claim. |
| 31 | full | Evidential Object and Navigation Audit - Full | Editorial Gate | Audit the semantic and technical integrity of figures, tables, equations, listings and cross-references. |
| 32 | full | Execution, Context and Provenance Record - Full | Execution Gate | Preserve lineage from starting state to candidate and accepted work. |
| 33 | full | Feasibility Sprint Record - Full | Problem Gate | Test a costly uncertainty through a bounded, safe and evidential action. |
| 34 | full | Gate Record — Full | Relevant gate | Record a complete gate disposition, including the strongest objection, unresolved authority, conditions and earliest return gate. |
| 35 | full | Milestone Evidence Register — Full | All gates | Map each milestone or gate to its required scientific, administrative or release record, current version, retained proof and missing-condition response. |
| 36 | full | Mock Defence And Recovery Record — Full | Defence Readiness Gate | Record unseen-question, evidence-retrieval, failure, fallback and incident tests and the recovery action they require. |
| 37 | full | Package Consistency Record — Full | Defence Readiness Gate | Test scientific-content identity across the authoritative source, official artefacts, evidence package, slides, demonstration and public-release candidate. |
| 38 | full | Presentation Spine Record — Full | Defence Readiness Gate | Compress the accepted argument into a timed, accessible and claim-bounded presentation without restoring rejected wording. |
| 39 | full | Project Start Pack - Full | Project Start Pack | Establish the product, route, access, authority, workspace and first controlled deliverable. |
| 40 | full | Risk and Assumption Register - Full | Design Gate | Make consequential assumptions, risks, mitigations and reopening triggers inspectable. |
| 41 | full | Route Selector - Full | Project Start Pack | Select a dominant route through evidence obligations rather than topic vocabulary. |
| 42 | full | SCOPE Canvas - Full | Problem Gate | Externalise scope, evidence, boundaries and uncertainty before commitment. |
| 43 | full | Search Strategy Record - Full | Evidence Gate | Make discovery routes, dates, strings and limits inspectable. |
| 44 | full | Section Contract Register - Full | Argument Gate | Assign each manuscript section an intellectual function, evidence set and boundary. |
| 45 | full | Similarity, AI and Authorship Record - Full | Editorial Gate | Separate similarity, attribution, text recycling, AI disclosure and oral ownership. |
| 46 | full | Source, Rights and Attribution Record - Full | Editorial Gate | Verify source identity, claim fitness, attribution and rights bidirectionally. |
| 47 | full | Submission Package Manifest - Full | Defence Readiness Gate | Separate institutional submission objects, private evidence and unpublished release candidates. |
| 48 | full | Synthesis Memo - Full | Evidence Gate | Convert source notes into a bounded pattern, contradiction or uncertainty. |
| 49 | full | TRACE Record - Full | All gates | Record consequential AI use from task to verification, disposition and disclosure. |
| 50 | full | Uncertainty and Counter-Evidence Record - Full | Claim Gate | Preserve uncertainty and evidence that resists the preferred interpretation. |
| 51 | full | Version and Manifest Record - Full | All closure gates | Preserve provenance, supersession and derivative identity for every controlled package. |
| 52 | full | Work-Unit Brief - Full | Execution Gate | Bound one authorised unit of execution and its admission criteria. |

Part A — Minimum records

Complete one minimum record before escalating. Minimum does not mean optional where the mapped decision is consequential.

A1. Claim-Evidence Map — Minimum

CSV: companion/03_TEMPLATES_MINIMUM/CLAIM_EVIDENCE_MAP_MIN.csv

Purpose. Make the exact wording, evidence, uncertainty, boundary and counter-evidence inspectable.

Use and completion. Add one row per inspectable object. Preserve stable identifiers and versions. No substantive claim remains without evidence or with an undeclared transfer boundary.

Boundary. controlled project metadata; no credentials, direct identifiers or confidential payloads Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | claim_id | Stable identifier for one exact claim wording. Validation: non-empty stable identifier; unique within the project namespace. |
| 2 | exact_claim_text | Exact sentence or proposition whose wording is being authorised or rejected. Validation: non-empty when required; internally consistent with linked records. |
| 3 | evidence_object | Stable identifier or safe locator for the evidence used. Do not paste confidential payloads. Validation: non-empty when required; internally consistent with linked records. |
| 4 | method_or_source | Verified source or identity information for method or source, sufficient for independent resolution. Validation: non-empty when required; internally consistent with linked records. |
| 5 | uncertainty | Statistical, numerical, measurement, interpretive, model or transfer uncertainty relevant to the decision. Validation: non-empty when required; internally consistent with linked records. |
| 6 | boundary | Explicit scope limit for population, case, corpus, time, environment, method or transfer. Validation: non-empty when required; internally consistent with linked records. |
| 7 | counter_evidence_or_alternative | Evidence or credible explanation that resists the preferred interpretation. Validation: non-empty when required; internally consistent with linked records. |
| 8 | stronger_wording_rejected | Attractive but unsupported wording that the evidence does not authorise. Validation: non-empty when required; internally consistent with linked records. |
| 9 | status | Current lifecycle or decision status. Use the controlled vocabulary declared for the record. Controlled values: candidate; supported conditionally; supported; narrowed; suspended; rejected. Validation: use one exact value from controlled vocabulary: claim_status. |

A2. CORPUS Ledger — Minimum

CSV: companion/03_TEMPLATES_MINIMUM/CORPUS_LEDGER_MIN.csv

Purpose. Resolve source identity and preserve the reason for inclusion, exclusion and use.

Use and completion. Add one row per inspectable object. Preserve stable identifiers and versions. Every load-bearing source has an identity, access route, appraisal and claim-linked use.

Boundary. bibliographic and source metadata only; do not redistribute restricted full texts Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | record_id | Stable identifier for the record. It must not change when the file is copied. Validation: non-empty stable identifier; unique within the project namespace. |
| 2 | citation_or_object | Verified source or identity information for citation or object, sufficient for independent resolution. Validation: non-empty when required; internally consistent with linked records. |
| 3 | source_class | Verified source or identity information for source class, sufficient for independent resolution. Validation: non-empty when required; internally consistent with linked records. |
| 4 | search_or_access_route | Reproducible route by which the source, study, artefact or other corpus item was located and accessed. Validation: non-empty when required; internally consistent with linked records. |
| 5 | identity_or_study_id | Resolved identity at the appropriate level, separating records, publications and studies when relevant. Validation: non-empty stable identifier; unique within the project namespace. |
| 6 | inclusion_status | Candidate, included, excluded, duplicate or superseded state for the source or object. Controlled values: candidate; included; excluded; duplicate; superseded. Validation: use one exact value from controlled vocabulary: inclusion_status. |
| 7 | appraisal | Recorded assessment of relevance, method fit, directness, consistency and decision usefulness for the declared evidence use. Validation: non-empty when required; internally consistent with linked records. |
| 8 | rights_or_access | Named authority, permission or rights basis governing rights or access. Validation: non-empty when required; internally consistent with linked records. |
| 9 | claim_or_decision_use | Exact bounded claim or claim-related role represented by claim or decision use. Validation: non-empty when required; internally consistent with linked records. |
| 10 | version | Explicit version identifier for the record or object. Do not rely on file modification time. Validation: explicit version or dated revision; no ambiguous labels such as final-final. |
| 11 | notes | Optional concise qualification that cannot be represented elsewhere; do not use it for unstructured personal or confidential payloads. Validation: non-empty when required; internally consistent with linked records. |

A3. DECIDE Record — Minimum

CSV: companion/03_TEMPLATES_MINIMUM/DECIDE_RECORD_MIN.csv

Purpose. Make one consequential decision conditional, evidence-linked and reopenable.

Use and completion. Add one row per inspectable object. Preserve stable identifiers and versions. A credible alternative, authority boundary, early test and reopening trigger are recorded.

Boundary. controlled project metadata; no credentials, direct identifiers or confidential payloads Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | decision_id | Stable identifier for one consequential decision. Validation: non-empty stable identifier; unique within the project namespace. |
| 2 | decision | Explicit disposition selected from the record’s controlled outcomes and justified by named evidence. Validation: non-empty when required; internally consistent with linked records. |
| 3 | credible_alternatives | Plausible competing decisions, routes or explanations considered before making the recorded commitment. Validation: non-empty when required; internally consistent with linked records. |
| 4 | criteria | Explicit criteria used to compare alternatives and authorise, narrow or reject the conditional commitment. Validation: non-empty when required; internally consistent with linked records. |
| 5 | evidence_and_authority | Named, retrievable evidence relevant to evidence and authority; use a safe locator rather than confidential payload. Validation: non-empty when required; internally consistent with linked records. |
| 6 | assumptions_and_risks | Material constraint, uncertainty or boundary associated with assumptions and risks. Validation: non-empty when required; internally consistent with linked records. |
| 7 | conditional_commitment | Current decision authorised only within named conditions, evidence limits and reopening triggers. Validation: non-empty when required; internally consistent with linked records. |
| 8 | early_test | Smallest safe test capable of falsifying, narrowing or redirecting the proposed commitment before full execution. Validation: non-empty when required; internally consistent with linked records. |
| 9 | reopening_trigger | Observable condition that invalidates or narrows the current commitment and reopens a named gate. Validation: non-empty when required; internally consistent with linked records. |
| 10 | reviewer | Named person or competent role that inspected the current version. Validation: non-empty when required; internally consistent with linked records. |
| 11 | date | ISO 8601 date on which the action, observation or disposition occurred. Validation: ISO 8601 date (YYYY-MM-DD). |
| 12 | status | Current lifecycle or decision status. Use the controlled vocabulary declared for the record. Controlled values: draft; candidate; reviewed; accepted locally; superseded; withdrawn. Validation: use one exact value from controlled vocabulary: lifecycle_status. |

A4. Defence Question Matrix — Minimum

CSV: companion/03_TEMPLATES_MINIMUM/DEFENCE_QUESTION_MATRIX_MIN.csv

Purpose. Prepare direct, evidence-anchored and bounded answers, including legitimate uncertainty.

Use and completion. Add one row per inspectable object. Preserve stable identifiers and versions. Every answer names an evidence anchor, a boundary and a follow-up challenge.

Boundary. may reference restricted administrative objects; store only safe identifiers and segregated locators Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | question_family | Exact question represented by question family. Validation: non-empty when required; internally consistent with linked records. |
| 2 | hostile_question | Realistic adversarial question that tests evidence, reasoning, uncertainty, authority or ownership. Validation: non-empty when required; internally consistent with linked records. |
| 3 | direct_answer | Concise answer that addresses the question before explanation and does not exceed the accepted claim. Validation: non-empty when required; internally consistent with linked records. |
| 4 | evidence_anchor | Named, retrievable evidence relevant to evidence anchor; use a safe locator rather than confidential payload. Validation: non-empty when required; internally consistent with linked records. |
| 5 | inferential_link | Reasoning step that connects the named evidence to the exact bounded claim or defence answer. Validation: non-empty when required; internally consistent with linked records. |
| 6 | limitation | Condition that materially restricts interpretation, transfer or use of the finding. Validation: non-empty when required; internally consistent with linked records. |
| 7 | what_does_not_follow | Attractive conclusion explicitly excluded by the evidence, design, uncertainty or route boundary. Validation: non-empty when required; internally consistent with linked records. |
| 8 | follow_up | Likely second question or challenge and the evidence needed to answer it without exceeding the accepted claim. Validation: non-empty when required; internally consistent with linked records. |
| 9 | rehearsal_status | State of independent rehearsal and unresolved defect, not a prediction of examination outcome. Controlled values: draft; candidate; reviewed; accepted locally; superseded; withdrawn. Validation: use one exact value from controlled vocabulary: lifecycle_status. |

A5. Demonstration Runbook — Minimum

CSV: companion/03_TEMPLATES_MINIMUM/DEMONSTRATION_RUNBOOK_MIN.csv

Purpose. Prepare a route-appropriate evidential demonstration with a safe fallback.

Use and completion. Add one row per inspectable object. Preserve stable identifiers and versions. The primary path, failure case and fallback use the same accepted release and do not imply a stronger claim.

Boundary. record versions and evidence locators, not secrets, personal data or proprietary payloads Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | step | Ordered action in the procedure or demonstration, stated at a level that permits rehearsal and independent repetition. Validation: non-empty when required; internally consistent with linked records. |
| 2 | purpose | Decision, claim, evidence obligation or reader task served by the step, record, slide or demonstration action. Validation: non-empty when required; internally consistent with linked records. |
| 3 | route | One of the eight locked inquiry routes or an explicitly justified hybrid component. Controlled values: build-and-evaluate; algorithmic or simulation study; predictive or machine-learning study; quantitative empirical study; qualitative inquiry; case study; formal evidence synthesis; hybrid route. Validation: use one exact value from controlled vocabulary: route. |
| 4 | release_or_state | Exact frozen release, commit, dataset, environment, manuscript or configuration state used for the step. Validation: non-empty when required; internally consistent with linked records. |
| 5 | action | Specific, owned and testable action for action. Validation: non-empty when required; internally consistent with linked records. |
| 6 | expected_evidence | Evidence object that should be produced if the step behaves as designed. Validation: non-empty when required; internally consistent with linked records. |
| 7 | failure_case | Known or rehearsed condition in which the primary path fails or the claim boundary is tested. Validation: non-empty when required; internally consistent with linked records. |
| 8 | fallback | Safe secondary path using the same accepted release and scientific claim boundary. Validation: non-empty when required; internally consistent with linked records. |
| 9 | reset_or_stop_rule | Condition for safe reset, containment or termination of the demonstration or work unit. Validation: non-empty when required; internally consistent with linked records. |
| 10 | time_boundary | Material constraint, uncertainty or boundary associated with time boundary. Validation: non-empty when required; internally consistent with linked records. |
| 11 | status | Current lifecycle or decision status. Use the controlled vocabulary declared for the record. Controlled values: draft; candidate; reviewed; accepted locally; superseded; withdrawn. Validation: use one exact value from controlled vocabulary: lifecycle_status. |

A6. Feasibility Sprint Record — Minimum

CSV: companion/03_TEMPLATES_MINIMUM/FEASIBILITY_SPRINT_RECORD_MIN.csv

Purpose. Test the most expensive uncertainty before full commitment.

Use and completion. Complete only when the current decision requires this record. The test produces inspectable evidence and one of continue, narrow, pivot or stop.

Boundary. controlled project metadata; no credentials, direct identifiers or confidential payloads Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | Critical uncertainty | Name the uncertainty with the greatest downstream cost. Validation: non-empty when required; internally consistent with linked records. |
| 2 | Bounded action | State the smallest safe test. Validation: non-empty when required; internally consistent with linked records. |
| 3 | Evidence produced | Name the retained evidence object. Validation: non-empty when required; internally consistent with linked records. |
| 4 | Acceptance criterion | State the criterion before reporting the outcome. Validation: non-empty when required; internally consistent with linked records. |
| 5 | Decision consequence | Continue, narrow, pivot or stop. Controlled values: continue; narrow; pivot; stop. Validation: non-empty when required; internally consistent with linked records. |
| 6 | Gate reopened if failed | Name the earliest responsible gate. Controlled values: Project Start Pack / opening control; Problem Gate; Evidence Gate; Design Gate; Execution Gate; Claim Gate; Argument Gate; Editorial Gate; Defence Readiness Gate. Validation: use one exact common gate/control name or an explicit justified external authority route where the record permits it. |
| 7 | Owner and dates | Responsible role, start date, review date and due date for the feasibility sprint; avoid personal contact details in a public-facing record. Validation: non-empty when required; internally consistent with linked records. |
| 8 | Version and status | Assign identifier, version and disposition. Validation: explicit version or dated revision; no ambiguous labels such as final-final. |

A7. Gate Record — Minimum

CSV: companion/03_TEMPLATES_MINIMUM/GATE_RECORD_MIN.csv

Purpose. Record the decision, evidence status, strongest objection and return route for one gate.

Use and completion. Add one row per inspectable object. Preserve stable identifiers and versions. The decision is justified by named objects and does not hide a missing authority or contradiction.

Boundary. controlled project metadata; no credentials, direct identifiers or confidential payloads Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | gate | Current gate or opening control under which the decision is being reviewed. Controlled values: Project Start Pack / opening control; Problem Gate; Evidence Gate; Design Gate; Execution Gate; Claim Gate; Argument Gate; Editorial Gate; Defence Readiness Gate. Validation: use one exact common gate/control name or an explicit justified external authority route where the record permits it. |
| 2 | decision_question | Exact question that the gate or control must answer before progression. Validation: non-empty when required; internally consistent with linked records. |
| 3 | required_objects | Stable identifiers or safe locators for every object required to answer the gate question. Validation: non-empty when required; internally consistent with linked records. |
| 4 | evidence_status | State of the required evidence: missing, candidate, verified, conditionally accepted or rejected. Controlled values: missing; candidate; verified; accepted conditionally; rejected. Validation: use one exact value from controlled vocabulary: evidence_status. |
| 5 | strongest_hostile_objection | Most consequential realistic objection a competent sceptical reviewer could raise against progression at the current gate. Validation: non-empty when required; internally consistent with linked records. |
| 6 | decision | Explicit disposition selected from the record’s controlled outcomes and justified by named evidence. Controlled values: pass; pass with conditions; repair; return; await authority; stop. Validation: use one exact value from controlled vocabulary: gate_decision. |
| 7 | named_actions | Specific, owned and testable action for named actions. Validation: non-empty when required; internally consistent with linked records. |
| 8 | return_route | Named earlier gate and observable trigger to which the project must return when the current decision does not hold. Controlled values: Project Start Pack / opening control; Problem Gate; Evidence Gate; Design Gate; Execution Gate; Claim Gate; Argument Gate; Editorial Gate; Defence Readiness Gate. Validation: use one exact common gate/control name or an explicit justified external authority route where the record permits it. |
| 9 | reviewer | Named person or competent role that inspected the current version. Validation: non-empty when required; internally consistent with linked records. |
| 10 | date | ISO 8601 date on which the action, observation or disposition occurred. Validation: ISO 8601 date (YYYY-MM-DD). |
| 11 | version | Explicit version identifier for the record or object. Do not rely on file modification time. Validation: explicit version or dated revision; no ambiguous labels such as final-final. |

A8. Project Start Pack — Minimum

CSV: companion/03_TEMPLATES_MINIMUM/PROJECT_START_PACK_MIN.csv

Purpose. Establish project identity, access, authority and the first reviewable product.

Use and completion. Complete only when the current decision requires this record. The project can be identified, the access boundary is explicit and a reviewer can authorise one next action.

Boundary. controlled project metadata; no credentials, direct identifiers or confidential payloads Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | Product | Name the assessed product. Validation: non-empty when required; internally consistent with linked records. |
| 2 | Working title | Use the exact current title. Validation: non-empty when required; internally consistent with linked records. |
| 3 | Problem | State the concrete problem and affected context. Validation: non-empty when required; internally consistent with linked records. |
| 4 | Provisional route | Select the dominant route. Controlled values: build-and-evaluate; algorithmic or simulation study; predictive or machine-learning study; quantitative empirical study; qualitative inquiry; case study; formal evidence synthesis; hybrid route. Validation: use one exact value from controlled vocabulary: route. |
| 5 | Access | Confirmed access boundary for the intended sources, data, environment, participants or artefacts, including named restrictions and unresolved dependencies. Validation: non-empty when required; internally consistent with linked records. |
| 6 | Authority | Name who can advise, approve access or impose a rule. Validation: non-empty when required; internally consistent with linked records. |
| 7 | First deliverable | Name one bounded object due next. Validation: non-empty when required; internally consistent with linked records. |
| 8 | Owner | Name the responsible student. Validation: non-empty when required; internally consistent with linked records. |
| 9 | Reviewer and date | Competent reviewing role and ISO 8601 review date for the current project-start record. Validation: ISO 8601 date (YYYY-MM-DD). |
| 10 | Version and status | Assign a stable identifier and status. Validation: explicit version or dated revision; no ambiguous labels such as final-final. |

A9. Route Selector — Minimum

CSV: companion/03_TEMPLATES_MINIMUM/ROUTE_SELECTOR_MIN.csv

Purpose. Select the dominant route and expose the immediate evidence obligation.

Use and completion. Complete only when the current decision requires this record. One dominant route is named, secondary components are explicit and the prohibited inference is recorded.

Boundary. controlled project metadata; no credentials, direct identifiers or confidential payloads Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | Assessed product | Project, bachelor’s thesis, master’s dissertation or formal evidence synthesis. Validation: non-empty when required; internally consistent with linked records. |
| 2 | Dominant route | Select one of the eight routes. Controlled values: build-and-evaluate; algorithmic or simulation study; predictive or machine-learning study; quantitative empirical study; qualitative inquiry; case study; formal evidence synthesis; hybrid route. Validation: use one exact value from controlled vocabulary: route. |
| 3 | Secondary component | Use only when it has a distinct evidence role. Validation: non-empty when required; internally consistent with linked records. |
| 4 | Unit of analysis | Name the artefact, participant, case, study, run, record or other unit. Validation: non-empty when required; internally consistent with linked records. |
| 5 | Core evidence object | Name the evidence that must exist before the principal claim can be made. Validation: non-empty when required; internally consistent with linked records. |
| 6 | Credible comparison or reference | Name the baseline, reference case, alternative account or protocol basis. Validation: non-empty when required; internally consistent with linked records. |
| 7 | Uncertainty or boundary | State the main limit that must remain visible. Validation: non-empty when required; internally consistent with linked records. |
| 8 | Prohibited inference | Write the attractive but unsupported claim that must not be made. Validation: non-empty when required; internally consistent with linked records. |
| 9 | Current gate | Name the gate currently being prepared. Controlled values: Project Start Pack / opening control; Problem Gate; Evidence Gate; Design Gate; Execution Gate; Claim Gate; Argument Gate; Editorial Gate; Defence Readiness Gate. Validation: use one exact common gate/control name or an explicit justified external authority route where the record permits it. |
| 10 | Single next record | Name the next record that will reduce the most consequential uncertainty. Validation: non-empty when required; internally consistent with linked records. |

A10. SCOPE Canvas — Minimum

CSV: companion/03_TEMPLATES_MINIMUM/SCOPE_CANVAS_MIN.csv

Purpose. Turn an attractive topic into a bounded, answerable and revisable problem.

Use and completion. Complete only when the current decision requires this record. The research question, evidence obligation and transfer boundary are mutually compatible.

Boundary. controlled project metadata; no credentials, direct identifiers or confidential payloads Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | Situation | What concrete context has been observed?. Validation: non-empty when required; internally consistent with linked records. |
| 2 | Concern | What consequential problem or gap exists?. Validation: non-empty when required; internally consistent with linked records. |
| 3 | Object | What artefact, population, corpus, process or case is studied?. Validation: non-empty when required; internally consistent with linked records. |
| 4 | Purpose | What will be built, tested, compared, explained or synthesised?. Validation: non-empty when required; internally consistent with linked records. |
| 5 | Evidence | What evidence could answer the question?. Validation: non-empty when required; internally consistent with linked records. |
| 6 | Boundary | What is excluded and where does transfer stop?. Validation: non-empty when required; internally consistent with linked records. |
| 7 | Contribution | What is the smallest defensible contribution?. Validation: non-empty when required; internally consistent with linked records. |
| 8 | Research question | Write one route-aligned question. Validation: non-empty when required; internally consistent with linked records. |
| 9 | Reopening trigger | What finding would force narrowing, pivoting or stopping?. Validation: non-empty when required; internally consistent with linked records. |

A11. TRACE Record — Minimum

CSV: companion/03_TEMPLATES_MINIMUM/TRACE_RECORD_MIN.csv

Purpose. Record consequential generative-AI assistance and its verification and disposition.

Use and completion. Add one row per inspectable object. Preserve stable identifiers and versions. The student can explain the task, supplied context, candidate output, independent basis and final decision.

Boundary. do not paste confidential prompts, participant data, credentials or restricted source content Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | use_id | Stable identifier for one consequential generative AI use event. Validation: non-empty stable identifier; unique within the project namespace. |
| 2 | task | Exact consequential task delegated to or assisted by the generative system. Validation: non-empty when required; internally consistent with linked records. |
| 3 | tool_and_version | Exact tool and version used for the recorded task. Validation: explicit version or dated revision; no ambiguous labels such as final-final. |
| 4 | context_supplied | Context supplied to the generative system, excluding unnecessary personal, confidential or rights-restricted material. Validation: non-empty when required; internally consistent with linked records. |
| 5 | candidate_output | Object produced by the work unit before inspection and disposition. Validation: non-empty when required; internally consistent with linked records. |
| 6 | independent_verification | Source, test, primary artefact or competent review path independent of the generating tool output. Validation: non-empty when required; internally consistent with linked records. |
| 7 | decision | Explicit disposition selected from the record’s controlled outcomes and justified by named evidence. Controlled values: accepted; modified; rejected. Validation: use one exact value from controlled vocabulary: ai_disposition. |
| 8 | effect_on_evidence_reasoning_or_wording | Named, retrievable evidence relevant to effect on evidence reasoning or wording; use a safe locator rather than confidential payload. Validation: non-empty when required; internally consistent with linked records. |
| 9 | disclosure_mapping | Location and wording class of the disclosure required for the consequential AI use, if disclosure is required. Validation: non-empty when required; internally consistent with linked records. |
| 10 | date | ISO 8601 date on which the action, observation or disposition occurred. Validation: ISO 8601 date (YYYY-MM-DD). |
| 11 | owner | Person responsible for the object or next action. Use a role rather than personal contact data when appropriate. Validation: non-empty when required; internally consistent with linked records. |

A12. Version and Manifest Record — Minimum

CSV: companion/03_TEMPLATES_MINIMUM/VERSION_MANIFEST_RECORD_MIN.csv

Purpose. Preserve one source of truth and identify every derivative.

Use and completion. Complete only when the current decision requires this record. The authoritative object, version, hash, derivatives, rights and privacy status can be reconstructed.

Boundary. controlled project metadata; no credentials, direct identifiers or confidential payloads Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | Authoritative object | Name the source-of-truth file. Validation: non-empty when required; internally consistent with linked records. |
| 2 | Version | Use an explicit version identifier. Validation: explicit version or dated revision; no ambiguous labels such as final-final. |
| 3 | Date | Use ISO date in filenames. Validation: ISO 8601 date (YYYY-MM-DD). |
| 4 | SHA-256 | Lowercase SHA-256 digest of the exact controlled file. Recalculate it whenever the file bytes change. Validation: non-empty when required; internally consistent with linked records. |
| 5 | Derived objects | List PDF, archive, slides or data derivatives. Validation: non-empty when required; internally consistent with linked records. |
| 6 | Content identity | Confirm the same question, evidence, result and limitation. Validation: non-empty when required; internally consistent with linked records. |
| 7 | Rights and privacy | Confirm access, licence, consent and redaction status. Validation: non-empty when required; internally consistent with linked records. |
| 8 | Status and next action | Name the current state and next authorised action. Validation: non-empty when required; internally consistent with linked records. |

Part B — Full records

Full records preserve the audit trail required when the decision is high-risk, disputed, route-complex, authority-dependent or difficult to reconstruct.

B1. Accessibility and Render Audit — Full

CSV: companion/04_TEMPLATES_FULL/ACCESSIBILITY_RENDER_AUDIT_FULL.csv

Purpose. Preserve structural accessibility and inspect the rendered object page by page.

Use and completion. Add one row per inspectable object. Preserve stable identifiers and versions. High-impact defects are absent, findings are classified and the proof is tied to the authoritative source.

Boundary. controlled project metadata; no credentials, direct identifiers or confidential payloads Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | check_id | Stable identifier for check id. Use a reproducible project naming convention. Validation: non-empty stable identifier; unique within the project namespace. |
| 2 | object_or_page | Exact file, page, slide, table, figure or other rendered object inspected by the audit. Validation: non-empty when required; internally consistent with linked records. |
| 3 | check_type | Specific technical, editorial or accessibility inspection applied to the named object. Validation: non-empty when required; internally consistent with linked records. |
| 4 | criterion | Single observable criterion against which the named object is inspected and judged. Validation: non-empty when required; internally consistent with linked records. |
| 5 | result | Observed result for result, recorded without inflating interpretation. Controlled values: pass; fail; not applicable; pending. Validation: use one exact value from controlled vocabulary: audit_result. |
| 6 | severity | Materiality of the identified defect: low, medium, high or blocking. Controlled values: low; medium; high; blocking. Validation: non-empty when required; internally consistent with linked records. |
| 7 | finding | Observed result for finding, recorded without inflating interpretation. Validation: non-empty when required; internally consistent with linked records. |
| 8 | remediation | Specific, owned and testable action for remediation. Validation: non-empty when required; internally consistent with linked records. |
| 9 | evidence_location | Authorised workspace path, repository-relative path or stable identifier from which the evidence can be retrieved. Validation: non-empty when required; internally consistent with linked records. |
| 10 | reviewer | Named person or competent role that inspected the current version. Validation: non-empty when required; internally consistent with linked records. |
| 11 | date | ISO 8601 date on which the action, observation or disposition occurred. Validation: ISO 8601 date (YYYY-MM-DD). |
| 12 | proof_hash | Cryptographic digest or controlled identifier for proof hash. Validation: 64 lowercase hexadecimal characters where a file digest applies. |

B2. Appraisal Record — Full

CSV: companion/04_TEMPLATES_FULL/APPRAISAL_RECORD_FULL.csv

Purpose. Separate relevance, authority, methodological quality and fitness for a particular claim.

Use and completion. Add one row per inspectable object. Preserve stable identifiers and versions. Appraisal judgements are explicit and do not collapse prestige into fitness.

Boundary. bibliographic and source metadata only; do not redistribute restricted full texts Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | record_id | Stable identifier for the record. It must not change when the file is copied. Validation: non-empty stable identifier; unique within the project namespace. |
| 2 | relevance | Extent to which the source or evidence addresses the exact problem, population, context, route and claim under review. Validation: non-empty when required; internally consistent with linked records. |
| 3 | authority_basis | Named authority, permission or rights basis governing authority basis. Validation: non-empty when required; internally consistent with linked records. |
| 4 | method_fit | Extent to which the source design or evidence-production method is appropriate for the project’s exact question and claim. Validation: non-empty when required; internally consistent with linked records. |
| 5 | risk_of_bias_or_limitation | Material constraint, uncertainty or boundary associated with risk of bias or limitation. Validation: non-empty when required; internally consistent with linked records. |
| 6 | directness | Degree to which the evidence addresses the exact claim, population, context, route and outcome rather than an adjacent proposition. Validation: non-empty when required; internally consistent with linked records. |
| 7 | consistency | Extent to which the source or evidence agrees with the wider controlled evidence body, including any material contradiction. Validation: non-empty when required; internally consistent with linked records. |
| 8 | currency_or_version | Explicit version, revision or dated state for currency or version. Validation: explicit version or dated revision; no ambiguous labels such as final-final. |
| 9 | claim_fitness | Exact bounded claim or claim-related role represented by claim fitness. Validation: non-empty when required; internally consistent with linked records. |
| 10 | decision_use | Downstream decision for which the appraised source or evidence is sufficiently fit, or explicitly not fit. Validation: non-empty when required; internally consistent with linked records. |
| 11 | reviewer | Named person or competent role that inspected the current version. Validation: non-empty when required; internally consistent with linked records. |
| 12 | date | ISO 8601 date on which the action, observation or disposition occurred. Validation: ISO 8601 date (YYYY-MM-DD). |

B3. Argument Spine Map — Full

CSV: companion/04_TEMPLATES_FULL/ARGUMENT_SPINE_MAP_FULL.csv

Purpose. Transform gate records into one bounded answer rather than a chronology.

Use and completion. Complete only when the current decision requires this record. The problem, position, method, evidence, claim, limitation and contribution form one reconstructible chain.

Boundary. controlled project metadata; no credentials, direct identifiers or confidential payloads Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | Thesis answer in one sentence | Bounded answer. Validation: non-empty when required; internally consistent with linked records. |
| 2 | Problem | Why the answer matters. Validation: non-empty when required; internally consistent with linked records. |
| 3 | Knowledge position | What the verified literature permits. Validation: non-empty when required; internally consistent with linked records. |
| 4 | Method actually executed | Not only planned method. Validation: non-empty when required; internally consistent with linked records. |
| 5 | Evidence body | Named objects. Validation: non-empty when required; internally consistent with linked records. |
| 6 | Principal claim | Exact wording. Validation: non-empty when required; internally consistent with linked records. |
| 7 | Uncertainty and limitation | Must constrain the claim. Validation: non-empty when required; internally consistent with linked records. |
| 8 | Contribution | What the work adds. Validation: non-empty when required; internally consistent with linked records. |
| 9 | Rejected stronger answer | Wording not supported. Validation: non-empty when required; internally consistent with linked records. |
| 10 | Gate records used | Stable IDs. Validation: non-empty when required; internally consistent with linked records. |
| 11 | Reader hand-off | How the answer is distributed through sections. Validation: non-empty when required; internally consistent with linked records. |
| 12 | Version and reviewer | Lifecycle record. Validation: explicit version or dated revision; no ambiguous labels such as final-final. |

B4. Authoritative File and Version Record — Full

CSV: companion/04_TEMPLATES_FULL/AUTHORITATIVE_FILE_VERSION_RECORD_FULL.csv

Purpose. Designate one source of truth and preserve derivative identity.

Use and completion. Complete only when the current decision requires this record. The authoritative DOCX and every derivative have versions, hashes, rights and proof state.

Boundary. controlled project metadata; no credentials, direct identifiers or confidential payloads Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | Authoritative object | Exact filename. Validation: non-empty when required; internally consistent with linked records. |
| 2 | Version | Semantic version or controlled project version. Validation: explicit version or dated revision; no ambiguous labels such as final-final. |
| 3 | Date | ISO date. Validation: ISO 8601 date (YYYY-MM-DD). |
| 4 | SHA-256 | Lowercase SHA-256 digest of the exact controlled file. Recalculate it whenever the file bytes change. Validation: non-empty when required; internally consistent with linked records. |
| 5 | Source master | Upstream object. Validation: non-empty when required; internally consistent with linked records. |
| 6 | Derived objects | PDF, archive, slides, data, figures or companion. Validation: non-empty when required; internally consistent with linked records. |
| 7 | Content identity check | Same question, evidence, result and limit. Validation: non-empty when required; internally consistent with linked records. |
| 8 | StoryRanges and fields state | Updated or pending. Validation: non-empty when required; internally consistent with linked records. |
| 9 | Proof state | Technical, Word proof, rejected or final candidate. Controlled values: not rendered; candidate; passed technical proof; failed; pending Microsoft Word proof. Validation: use one exact value from controlled vocabulary: render_status. |
| 10 | Rights and privacy | Status. Validation: non-empty when required; internally consistent with linked records. |
| 11 | Supersedes | Prior version. Validation: non-empty when required; internally consistent with linked records. |
| 12 | Owner, reviewer and next action | Lifecycle record. Validation: non-empty when required; internally consistent with linked records. |

B5. Authority Matrix — Full

CSV: companion/04_TEMPLATES_FULL/AUTHORITY_MATRIX_FULL.csv

Purpose. Separate advice, academic approval, ethics, data ownership, security and licence authority.

Use and completion. Add one row per inspectable object. Preserve stable identifiers and versions. No approval is used as a substitute for a different authority route.

Boundary. may reference restricted administrative objects; store only safe identifiers and segregated locators Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | authority_id | Stable identifier for authority id. Use a reproducible project naming convention. Validation: non-empty stable identifier; unique within the project namespace. |
| 2 | decision_or_resource | Verified source or identity information for decision or resource, sufficient for independent resolution. Validation: non-empty when required; internally consistent with linked records. |
| 3 | authority_type | Named authority, permission or rights basis governing authority type. Validation: non-empty when required; internally consistent with linked records. |
| 4 | named_role_or_body | Exact competent role, office, committee, publisher or institutional body from which authority is claimed. Validation: non-empty when required; internally consistent with linked records. |
| 5 | basis_or_source | Verified source or identity information for basis or source, sufficient for independent resolution. Validation: non-empty when required; internally consistent with linked records. |
| 6 | status | Current lifecycle or decision status. Use the controlled vocabulary declared for the record. Controlled values: current; pending verification; conflict; superseded; broken link. Validation: use one exact value from controlled vocabulary: source_status. |
| 7 | conditions | Operational conditions, restrictions, dependencies or time limits imposed by the named authority. Validation: non-empty when required; internally consistent with linked records. |
| 8 | evidence_object | Stable identifier or safe locator for the evidence used. Do not paste confidential payloads. Validation: non-empty when required; internally consistent with linked records. |
| 9 | expiry_or_recheck | Date or observable trigger at which the authority record must be reverified before further operational use. Validation: non-empty when required; internally consistent with linked records. |
| 10 | owner | Person responsible for the object or next action. Use a role rather than personal contact data when appropriate. Validation: non-empty when required; internally consistent with linked records. |
| 11 | notes | Optional concise qualification that cannot be represented elsewhere; do not use it for unstructured personal or confidential payloads. Validation: non-empty when required; internally consistent with linked records. |

B6. Author Identity and Headline Consistency Record — Full

CSV: companion/04_TEMPLATES_FULL/AUTHOR_IDENTITY_HEADLINE_RECORD_FULL.csv

Purpose. Lock author order and headline layers to one study identity.

Use and completion. Complete only when the current decision requires this record. Title, abstract, keywords, contribution, conclusion and metadata describe the same bounded study.

Boundary. controlled project metadata; no credentials, direct identifiers or confidential payloads Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | Author order | Exact final order. Validation: non-empty when required; internally consistent with linked records. |
| 2 | Author identifiers | Only verified affiliations and ORCIDs. Validation: non-empty when required; internally consistent with linked records. |
| 3 | Contribution statement | Only confirmed contributions. Validation: non-empty when required; internally consistent with linked records. |
| 4 | Title | Bounded and accurate. Validation: non-empty when required; internally consistent with linked records. |
| 5 | Subtitle | If used. Validation: non-empty when required; internally consistent with linked records. |
| 6 | Abstract question | Matches manuscript. Validation: non-empty when required; internally consistent with linked records. |
| 7 | Abstract method | Executed method. Validation: non-empty when required; internally consistent with linked records. |
| 8 | Abstract result | Evidence-aligned. Validation: non-empty when required; internally consistent with linked records. |
| 9 | Abstract conclusion | Bounded claim. Validation: non-empty when required; internally consistent with linked records. |
| 10 | Keywords | Stable terminology. Validation: non-empty when required; internally consistent with linked records. |
| 11 | Conclusion wording | Does not restore rejected claim. Validation: non-empty when required; internally consistent with linked records. |
| 12 | File and repository metadata | Same identity. Validation: non-empty when required; internally consistent with linked records. |
| 13 | Verification and version | Reviewer, date and status. Validation: explicit version or dated revision; no ambiguous labels such as final-final. |

B7. Candidate Artefact and Inspection Record — Full

CSV: companion/04_TEMPLATES_FULL/CANDIDATE_ARTEFACT_INSPECTION_RECORD_FULL.csv

Purpose. Inspect the primary artefact rather than a summary or dashboard.

Use and completion. Complete only when the current decision requires this record. The object is identified, inspected against declared criteria and given an explicit disposition.

Boundary. record versions and evidence locators, not secrets, personal data or proprietary payloads Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | Candidate identifier | Stable ID. Validation: non-empty when required; internally consistent with linked records. |
| 2 | Object and version | Primary artefact. Validation: explicit version or dated revision; no ambiguous labels such as final-final. |
| 3 | Work-unit link | Authorised unit. Validation: non-empty when required; internally consistent with linked records. |
| 4 | Inspection basis | Specification, protocol, reference, known case or reviewer basis. Validation: non-empty when required; internally consistent with linked records. |
| 5 | Checks performed | Route-appropriate checks. Validation: non-empty when required; internally consistent with linked records. |
| 6 | Failed or adverse cases | Retained evidence. Validation: non-empty when required; internally consistent with linked records. |
| 7 | External effects | Network, file system, participant, organisational or other effects. Validation: non-empty when required; internally consistent with linked records. |
| 8 | Secrets, privacy and licences | Status and remediation. Validation: non-empty when required; internally consistent with linked records. |
| 9 | Deviations | Difference from approved plan. Validation: non-empty when required; internally consistent with linked records. |
| 10 | Disposition | Accept locally, repair, repeat, reject, defer or quarantine. Controlled values: accept locally; repair; repeat; reject; defer; quarantine. Validation: use one exact value from controlled vocabulary: work_disposition. |
| 11 | Reason | Evidence-based justification. Validation: non-empty when required; internally consistent with linked records. |
| 12 | Reviewer, date and version | Lifecycle record. Validation: explicit version or dated revision; no ambiguous labels such as final-final. |

B8. Claim-Evidence Map — Full

CSV: companion/04_TEMPLATES_FULL/CLAIM_EVIDENCE_MAP_FULL.csv

Purpose. Map each exact claim to evidence, reasoning, uncertainty, boundary and rejected stronger wording.

Use and completion. Add one row per inspectable object. Preserve stable identifiers and versions. Every substantive claim has a reconstructible evidence path and a status.

Boundary. controlled project metadata; no credentials, direct identifiers or confidential payloads Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | claim_id | Stable identifier for one exact claim wording. Validation: non-empty stable identifier; unique within the project namespace. |
| 2 | exact_claim_text | Exact sentence or proposition whose wording is being authorised or rejected. Validation: non-empty when required; internally consistent with linked records. |
| 3 | claim_type | Exact bounded claim or claim-related role represented by claim type. Validation: non-empty when required; internally consistent with linked records. |
| 4 | evidence_object | Stable identifier or safe locator for the evidence used. Do not paste confidential payloads. Validation: non-empty when required; internally consistent with linked records. |
| 5 | method_or_source | Verified source or identity information for method or source, sufficient for independent resolution. Validation: non-empty when required; internally consistent with linked records. |
| 6 | inferential_link | Reasoning step that connects the named evidence to the exact bounded claim or defence answer. Validation: non-empty when required; internally consistent with linked records. |
| 7 | uncertainty | Statistical, numerical, measurement, interpretive, model or transfer uncertainty relevant to the decision. Validation: non-empty when required; internally consistent with linked records. |
| 8 | boundary | Explicit scope limit for population, case, corpus, time, environment, method or transfer. Validation: non-empty when required; internally consistent with linked records. |
| 9 | counter_evidence | Named, retrievable evidence relevant to counter evidence; use a safe locator rather than confidential payload. Validation: non-empty when required; internally consistent with linked records. |
| 10 | stronger_wording_rejected | Attractive but unsupported wording that the evidence does not authorise. Validation: non-empty when required; internally consistent with linked records. |
| 11 | contribution_link | Explicit reasoning link between the evidence-supported claim and the bounded contribution asserted by the project. Validation: non-empty when required; internally consistent with linked records. |
| 12 | status | Current lifecycle or decision status. Use the controlled vocabulary declared for the record. Controlled values: candidate; supported conditionally; supported; narrowed; suspended; rejected. Validation: use one exact value from controlled vocabulary: claim_status. |
| 13 | reviewer | Named person or competent role that inspected the current version. Validation: non-empty when required; internally consistent with linked records. |
| 14 | version | Explicit version identifier for the record or object. Do not rely on file modification time. Validation: explicit version or dated revision; no ambiguous labels such as final-final. |

B9. Core Source Note — Full

CSV: companion/04_TEMPLATES_FULL/CORE_SOURCE_NOTE_FULL.csv

Purpose. Record what a load-bearing source actually supports and where its scope ends.

Use and completion. Complete only when the current decision requires this record. The source cannot be cited for a broader claim than the note permits.

Boundary. bibliographic and source metadata only; do not redistribute restricted full texts Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | Record identifier | Link to CORPUS. Validation: non-empty when required; internally consistent with linked records. |
| 2 | Verified source identity | Authors, date, title, venue, DOI or official URL. Validation: non-empty when required; internally consistent with linked records. |
| 3 | Source class | Study, standard, regulation, documentation, dataset or other. Validation: non-empty when required; internally consistent with linked records. |
| 4 | Question addressed | What the source investigates or governs. Validation: non-empty when required; internally consistent with linked records. |
| 5 | Method or authority basis | How the source produces knowledge or authority. Validation: non-empty when required; internally consistent with linked records. |
| 6 | Population, case or scope | Source-specific boundary. Validation: non-empty when required; internally consistent with linked records. |
| 7 | Finding or requirement | Precise statement in paraphrase. Validation: non-empty when required; internally consistent with linked records. |
| 8 | Load-bearing use | Claim or decision it supports. Validation: non-empty when required; internally consistent with linked records. |
| 9 | What it does not support | Explicit source-fit boundary. Validation: non-empty when required; internally consistent with linked records. |
| 10 | Contradictions or caveats | Internal or external limitations. Validation: non-empty when required; internally consistent with linked records. |
| 11 | Version or current status | Retraction, update, supersession or amendment status. Validation: explicit version or dated revision; no ambiguous labels such as final-final. |
| 12 | Reader verification | Location in original and verification date. Validation: non-empty when required; internally consistent with linked records. |

B10. CORPUS Ledger — Full

CSV: companion/04_TEMPLATES_FULL/CORPUS_LEDGER_FULL.csv

Purpose. Resolve each candidate object from discovery record to claim-linked use.

Use and completion. Add one row per inspectable object. Preserve stable identifiers and versions. Every load-bearing object has a verified identity, appraisal, access status and study-level mapping where relevant.

Boundary. bibliographic and source metadata only; do not redistribute restricted full texts Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | record_id | Stable identifier for the record. It must not change when the file is copied. Validation: non-empty stable identifier; unique within the project namespace. |
| 2 | citation_or_object | Verified source or identity information for citation or object, sufficient for independent resolution. Validation: non-empty when required; internally consistent with linked records. |
| 3 | source_class | Verified source or identity information for source class, sufficient for independent resolution. Validation: non-empty when required; internally consistent with linked records. |
| 4 | discovery_route | Database, catalogue, snowballing path, registry, repository or other route through which the item was found. Validation: non-empty when required; internally consistent with linked records. |
| 5 | identifier | Stable identifier for identifier. Use a reproducible project naming convention. Validation: non-empty stable identifier; unique within the project namespace. |
| 6 | record_id_external | Stable identifier assigned by an external database, repository, registry, publisher or institutional system. Validation: non-empty when required; internally consistent with linked records. |
| 7 | publication_id | Stable identifier for publication id. Use a reproducible project naming convention. Validation: non-empty stable identifier; unique within the project namespace. |
| 8 | study_id | Stable identifier for study id. Use a reproducible project naming convention. Validation: non-empty stable identifier; unique within the project namespace. |
| 9 | version_or_status | Explicit version, revision or dated state for version or status. Validation: explicit version or dated revision; no ambiguous labels such as final-final. |
| 10 | inclusion_status | Candidate, included, excluded, duplicate or superseded state for the source or object. Controlled values: candidate; included; excluded; duplicate; superseded. Validation: use one exact value from controlled vocabulary: inclusion_status. |
| 11 | reason | Specific inclusion, exclusion, duplication, supersession or other disposition rationale supported by the record. Validation: non-empty when required; internally consistent with linked records. |
| 12 | full_text_status | Current controlled status for full text status. Controlled values: pending verification; available; available with conditions; restricted; unavailable; not applicable. Validation: use one exact value from controlled vocabulary: access_status. |
| 13 | appraisal | Recorded assessment of relevance, method fit, directness, consistency and decision usefulness for the declared evidence use. Validation: non-empty when required; internally consistent with linked records. |
| 14 | rights_or_access | Named authority, permission or rights basis governing rights or access. Validation: non-empty when required; internally consistent with linked records. |
| 15 | claim_or_decision_use | Exact bounded claim or claim-related role represented by claim or decision use. Validation: non-empty when required; internally consistent with linked records. |
| 16 | notes | Optional concise qualification that cannot be represented elsewhere; do not use it for unstructured personal or confidential payloads. Validation: non-empty when required; internally consistent with linked records. |

B11. Current Session Authority Record — Full

CSV: companion/04_TEMPLATES_FULL/CURRENT_SESSION_AUTHORITY_RECORD_FULL.csv

Purpose. Separate dated official sources, operational values, conflicts, clarifications and recheck dates for the current route and session.

Use and completion. Use before relying on a deadline, form, route, portal instruction, examination condition or official exception. The operative value is traceable to a current source or named written clarification and conflicts are not concealed.

Boundary. may reference restricted administrative objects; store only safe identifiers and segregated locators Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | record_id | Stable identifier for the record. It must not change when the file is copied. Validation: non-empty stable identifier; unique within the project namespace. |
| 2 | route | One of the eight locked inquiry routes or an explicitly justified hybrid component. Controlled values: build-and-evaluate; algorithmic or simulation study; predictive or machine-learning study; quantitative empirical study; qualitative inquiry; case study; formal evidence synthesis; hybrid route. Validation: use one exact value from controlled vocabulary: route. |
| 3 | session | Exact academic session, call, edition or operational period to which the authority value applies. Validation: non-empty when required; internally consistent with linked records. |
| 4 | authority_level | Named authority, permission or rights basis governing authority level. Validation: non-empty when required; internally consistent with linked records. |
| 5 | official_source | Verified source or identity information for official source, sufficient for independent resolution. Validation: non-empty when required; internally consistent with linked records. |
| 6 | source_url | Official or original source locator. Record a verification date and do not treat the URL alone as proof of currency. Validation: absolute official/original URL plus verified_on and status in the same record. |
| 7 | revision_or_date | ISO 8601 date associated with revision or date. Validation: ISO 8601 date (YYYY-MM-DD). |
| 8 | verified_on | ISO 8601 date associated with verified on. Validation: ISO 8601 date (YYYY-MM-DD). |
| 9 | operational_value | Current value, requirement, date, locator or instruction extracted from the verified authority source. Validation: non-empty when required; internally consistent with linked records. |
| 10 | status | Current lifecycle or decision status. Use the controlled vocabulary declared for the record. Controlled values: current; pending verification; conflict; superseded; broken link. Validation: use one exact value from controlled vocabulary: source_status. |
| 11 | conflict | Specific discrepancy between sources, versions, authorities or operational values. Validation: non-empty when required; internally consistent with linked records. |
| 12 | clarification_owner | Named role responsible for obtaining competent written clarification. Validation: non-empty when required; internally consistent with linked records. |
| 13 | retained_evidence | Named, retrievable evidence relevant to retained evidence; use a safe locator rather than confidential payload. Validation: non-empty when required; internally consistent with linked records. |
| 14 | next_check | Date or trigger for re-verifying a volatile source or decision. Validation: non-empty when required; internally consistent with linked records. |

B12. DECIDE Record — Full

CSV: companion/04_TEMPLATES_FULL/DECIDE_RECORD_FULL.csv

Purpose. Record a consequential decision as a conditional commitment.

Use and completion. Complete only when the current decision requires this record. Alternatives, evidence, authority, adverse consequences, early test and reopening trigger are explicit.

Boundary. controlled project metadata; no credentials, direct identifiers or confidential payloads Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | Decision identifier | Stable ID. Validation: non-empty when required; internally consistent with linked records. |
| 2 | Define | State the decision in one sentence. Validation: non-empty when required; internally consistent with linked records. |
| 3 | Establish | Evidence and authority boundary. Validation: non-empty when required; internally consistent with linked records. |
| 4 | Construct | Credible alternatives, including a simpler option. Validation: non-empty when required; internally consistent with linked records. |
| 5 | Inspect | Assumptions, risks, adverse consequences and reversibility. Validation: non-empty when required; internally consistent with linked records. |
| 6 | Decide conditionally | Selected alternative and trade-off. Validation: non-empty when required; internally consistent with linked records. |
| 7 | Evaluate early | Test and acceptance criterion. Validation: non-empty when required; internally consistent with linked records. |
| 8 | Reopening trigger | Result that invalidates or narrows the decision. Validation: non-empty when required; internally consistent with linked records. |
| 9 | Affected objects | Plan, method, data, evaluation, claim and records. Validation: non-empty when required; internally consistent with linked records. |
| 10 | Owner | Responsible student. Validation: non-empty when required; internally consistent with linked records. |
| 11 | Reviewer or authority | Role and decision. Validation: non-empty when required; internally consistent with linked records. |
| 12 | Date, version and status | Lifecycle record. Validation: explicit version or dated revision; no ambiguous labels such as final-final. |

B13. Defence Question Matrix — Full

CSV: companion/04_TEMPLATES_FULL/DEFENCE_QUESTION_MATRIX_FULL.csv

Purpose. Prepare evidence-return answers to realistic hostile questions.

Use and completion. Add one row per inspectable object. Preserve stable identifiers and versions. Each answer identifies the claim, evidence, inferential link, uncertainty and boundary.

Boundary. may reference restricted administrative objects; store only safe identifiers and segregated locators Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | question_id | Stable identifier for one defence or review question. Validation: non-empty stable identifier; unique within the project namespace. |
| 2 | question_family | Exact question represented by question family. Validation: non-empty when required; internally consistent with linked records. |
| 3 | hostile_question | Realistic adversarial question that tests evidence, reasoning, uncertainty, authority or ownership. Validation: non-empty when required; internally consistent with linked records. |
| 4 | claim_at_issue | Exact bounded claim or claim-related role represented by claim at issue. Validation: non-empty when required; internally consistent with linked records. |
| 5 | direct_answer | Concise answer that addresses the question before explanation and does not exceed the accepted claim. Validation: non-empty when required; internally consistent with linked records. |
| 6 | evidence_anchor | Named, retrievable evidence relevant to evidence anchor; use a safe locator rather than confidential payload. Validation: non-empty when required; internally consistent with linked records. |
| 7 | inferential_link | Reasoning step that connects the named evidence to the exact bounded claim or defence answer. Validation: non-empty when required; internally consistent with linked records. |
| 8 | uncertainty | Statistical, numerical, measurement, interpretive, model or transfer uncertainty relevant to the decision. Validation: non-empty when required; internally consistent with linked records. |
| 9 | limitation | Condition that materially restricts interpretation, transfer or use of the finding. Validation: non-empty when required; internally consistent with linked records. |
| 10 | what_does_not_follow | Attractive conclusion explicitly excluded by the evidence, design, uncertainty or route boundary. Validation: non-empty when required; internally consistent with linked records. |
| 11 | follow_up | Likely second question or challenge and the evidence needed to answer it without exceeding the accepted claim. Validation: non-empty when required; internally consistent with linked records. |
| 12 | reviewer | Named person or competent role that inspected the current version. Validation: non-empty when required; internally consistent with linked records. |
| 13 | rehearsal_status | State of independent rehearsal and unresolved defect, not a prediction of examination outcome. Controlled values: draft; candidate; reviewed; accepted locally; superseded; withdrawn. Validation: use one exact value from controlled vocabulary: lifecycle_status. |

B14. Defence Readiness Record — Full

CSV: companion/04_TEMPLATES_FULL/DEFENCE_READINESS_RECORD_FULL.csv

Purpose. Record whether the scientific record, submitted package, demonstration, slides and oral account preserve one contribution.

Use and completion. Complete only when the current decision requires this record. An independent reviewer can retrieve the evidence, challenge the claim and verify disclosures without version drift.

Boundary. may reference restricted administrative objects; store only safe identifiers and segregated locators Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | Scientific record version | Exact ID and hash. Validation: explicit version or dated revision; no ambiguous labels such as final-final. |
| 2 | Institutional package version | Exact ID and manifest. Validation: explicit version or dated revision; no ambiguous labels such as final-final. |
| 3 | Private defence evidence set | Restricted inventory. Validation: non-empty when required; internally consistent with linked records. |
| 4 | Public-release candidate | Unpublished status and exclusions. Validation: non-empty when required; internally consistent with linked records. |
| 5 | Presentation version | Exact ID and hash. Validation: explicit version or dated revision; no ambiguous labels such as final-final. |
| 6 | Demonstration runbook | Accepted release and fallback. Validation: non-empty when required; internally consistent with linked records. |
| 7 | Independent rehearsal | Reviewer and unseen questions. Validation: non-empty when required; internally consistent with linked records. |
| 8 | Evidence retrieval test | Time and result. Validation: non-empty when required; internally consistent with linked records. |
| 9 | Hostile-question outcome | Bounded answers and unresolved items. Validation: non-empty when required; internally consistent with linked records. |
| 10 | AI disclosure and oral ownership | Status. Validation: non-empty when required; internally consistent with linked records. |
| 11 | Rights, privacy and authority | Current status. Validation: non-empty when required; internally consistent with linked records. |
| 12 | Gate decision | Pass, conditional pass, repair, return, await authority or stop. Controlled values: pass; pass with conditions; repair; return; await authority; stop. Validation: use one exact value from controlled vocabulary: gate_decision. |
| 13 | Next action, reviewer, date and version | Lifecycle record. Validation: explicit version or dated revision; no ambiguous labels such as final-final. |

B15. Demonstration Runbook — Full

CSV: companion/04_TEMPLATES_FULL/DEMONSTRATION_RUNBOOK_FULL.csv

Purpose. Prepare a route-specific evidential demonstration, failure case and fallback.

Use and completion. Add one row per inspectable object. Preserve stable identifiers and versions. The demonstration is tied to the accepted evidence and cannot imply a stronger claim.

Boundary. record versions and evidence locators, not secrets, personal data or proprietary payloads Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | step | Ordered action in the procedure or demonstration, stated at a level that permits rehearsal and independent repetition. Validation: non-empty when required; internally consistent with linked records. |
| 2 | route | One of the eight locked inquiry routes or an explicitly justified hybrid component. Controlled values: build-and-evaluate; algorithmic or simulation study; predictive or machine-learning study; quantitative empirical study; qualitative inquiry; case study; formal evidence synthesis; hybrid route. Validation: use one exact value from controlled vocabulary: route. |
| 3 | purpose | Decision, claim, evidence obligation or reader task served by the step, record, slide or demonstration action. Validation: non-empty when required; internally consistent with linked records. |
| 4 | claim_served | Exact bounded claim or claim-related role represented by claim served. Validation: non-empty when required; internally consistent with linked records. |
| 5 | release_or_state | Exact frozen release, commit, dataset, environment, manuscript or configuration state used for the step. Validation: non-empty when required; internally consistent with linked records. |
| 6 | environment | Exact hardware, operating system, software, runtime and material conditions needed to execute or demonstrate the step. Validation: non-empty when required; internally consistent with linked records. |
| 7 | action | Specific, owned and testable action for action. Validation: non-empty when required; internally consistent with linked records. |
| 8 | expected_evidence | Evidence object that should be produced if the step behaves as designed. Validation: non-empty when required; internally consistent with linked records. |
| 9 | failure_case | Known or rehearsed condition in which the primary path fails or the claim boundary is tested. Validation: non-empty when required; internally consistent with linked records. |
| 10 | secondary_path | Rehearsed alternate path that preserves the same accepted release, evidence and claim boundary if the primary path fails. Validation: non-empty when required; internally consistent with linked records. |
| 11 | fallback | Safe secondary path using the same accepted release and scientific claim boundary. Validation: non-empty when required; internally consistent with linked records. |
| 12 | reset_or_stop_rule | Condition for safe reset, containment or termination of the demonstration or work unit. Validation: non-empty when required; internally consistent with linked records. |
| 13 | time_boundary | Material constraint, uncertainty or boundary associated with time boundary. Validation: non-empty when required; internally consistent with linked records. |
| 14 | owner | Person responsible for the object or next action. Use a role rather than personal contact data when appropriate. Validation: non-empty when required; internally consistent with linked records. |
| 15 | status | Current lifecycle or decision status. Use the controlled vocabulary declared for the record. Controlled values: draft; candidate; reviewed; accepted locally; superseded; withdrawn. Validation: use one exact value from controlled vocabulary: lifecycle_status. |

B16. Early Test Record — Full

CSV: companion/04_TEMPLATES_FULL/EARLY_TEST_RECORD_FULL.csv

Purpose. Test one consequential design commitment before full execution.

Use and completion. Complete only when the current decision requires this record. The test result can confirm conditionally, repair, invalidate or await authority.

Boundary. controlled project metadata; no credentials, direct identifiers or confidential payloads Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | Test identifier | Stable ID. Validation: non-empty when required; internally consistent with linked records. |
| 2 | Commitment tested | Link to DECIDE. Validation: non-empty when required; internally consistent with linked records. |
| 3 | Question | What uncertainty is tested. Validation: non-empty when required; internally consistent with linked records. |
| 4 | Starting state | Version, data and environment. Validation: non-empty when required; internally consistent with linked records. |
| 5 | Method | Bounded test. Validation: non-empty when required; internally consistent with linked records. |
| 6 | Authority and safety | Permissions and containment. Validation: non-empty when required; internally consistent with linked records. |
| 7 | Acceptance criterion | Declared before test. Validation: non-empty when required; internally consistent with linked records. |
| 8 | Observed result | Evidence, not inflated conclusion. Validation: non-empty when required; internally consistent with linked records. |
| 9 | Disposition | Confirm conditionally, repair, invalidate or await authority. Controlled values: accept locally; repair; repeat; reject; defer; quarantine. Validation: use one exact value from controlled vocabulary: work_disposition. |
| 10 | Reopening trigger | Gate and object. Validation: non-empty when required; internally consistent with linked records. |
| 11 | Evidence location | Stable path or identifier. Validation: non-empty when required; internally consistent with linked records. |
| 12 | Owner, reviewer, date and version | Lifecycle record. Validation: explicit version or dated revision; no ambiguous labels such as final-final. |

B17. Editorial Revision Map — Full

CSV: companion/04_TEMPLATES_FULL/EDITORIAL_REVISION_MAP_FULL.csv

Purpose. Control meaning-changing and technically consequential edits by location, scale, authority, return gate and retest.

Use and completion. Use when an edit can affect the question, method, evidence, claim, source, right, field, figure, table or proof state. Every consequential revision has an authorised action, effect analysis, retest and final disposition.

Boundary. controlled project metadata; no credentials, direct identifiers or confidential payloads Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | revision_id | Stable identifier for revision id. Use a reproducible project naming convention. Validation: non-empty stable identifier; unique within the project namespace. |
| 2 | location | Exact chapter, section, table, figure, paragraph, file or record location affected by the revision. Validation: non-empty when required; internally consistent with linked records. |
| 3 | semantic_scale | Extent of meaning affected by the revision: local wording, paragraph, section, chapter, cross-book architecture or companion contract. Validation: non-empty when required; internally consistent with linked records. |
| 4 | defect | Exact editorial, semantic, evidential or navigational defect that the revision must remove. Validation: non-empty when required; internally consistent with linked records. |
| 5 | evidence_or_rule | Named, retrievable evidence relevant to evidence or rule; use a safe locator rather than confidential payload. Validation: non-empty when required; internally consistent with linked records. |
| 6 | authorised_action | Specific, owned and testable action for authorised action. Validation: non-empty when required; internally consistent with linked records. |
| 7 | claim_or_method_effect | Exact bounded claim or claim-related role represented by claim or method effect. Validation: non-empty when required; internally consistent with linked records. |
| 8 | earliest_return_gate | Earliest gate responsible for the defect. Later-stage repair must not conceal earlier scientific drift. Controlled values: Project Start Pack / opening control; Problem Gate; Evidence Gate; Design Gate; Execution Gate; Claim Gate; Argument Gate; Editorial Gate; Defence Readiness Gate. Validation: use one exact common gate/control name or an explicit justified external authority route where the record permits it. |
| 9 | owner | Person responsible for the object or next action. Use a role rather than personal contact data when appropriate. Validation: non-empty when required; internally consistent with linked records. |
| 10 | status | Current lifecycle or decision status. Use the controlled vocabulary declared for the record. Controlled values: draft; candidate; reviewed; accepted locally; superseded; withdrawn. Validation: use one exact value from controlled vocabulary: lifecycle_status. |
| 11 | retest | Specific inspection that must be repeated after the revision and the evidence required to close the defect. Validation: non-empty when required; internally consistent with linked records. |
| 12 | date | ISO 8601 date on which the action, observation or disposition occurred. Validation: ISO 8601 date (YYYY-MM-DD). |
| 13 | version | Explicit version identifier for the record or object. Do not rely on file modification time. Validation: explicit version or dated revision; no ambiguous labels such as final-final. |

B18. Evaluation Design Record — Full

CSV: companion/04_TEMPLATES_FULL/EVALUATION_DESIGN_RECORD_FULL.csv

Purpose. Design evaluation backwards from the minimum meaningful claim.

Use and completion. Complete only when the current decision requires this record. The comparison, evidence body, uncertainty, counter-evidence and forbidden inference are declared before interpretation.

Boundary. controlled project metadata; no credentials, direct identifiers or confidential payloads Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | Evaluation identifier | Stable ID. Validation: non-empty when required; internally consistent with linked records. |
| 2 | Minimum meaningful claim | Exact candidate wording. Validation: non-empty when required; internally consistent with linked records. |
| 3 | Consequence if wrong | Why the claim deserves scrutiny. Validation: non-empty when required; internally consistent with linked records. |
| 4 | Route and unit | Route-specific evaluation object. Validation: non-empty when required; internally consistent with linked records. |
| 5 | Comparison or reference | Baseline, case, counterfactual, reference or synthesis basis. Validation: non-empty when required; internally consistent with linked records. |
| 6 | Evidence body | All required evidence objects. Validation: non-empty when required; internally consistent with linked records. |
| 7 | Metrics, estimates or analytic outputs | With units and definitions. Validation: non-empty when required; internally consistent with linked records. |
| 8 | Uncertainty | Statistical, numerical, interpretive, measurement or transfer. Validation: non-empty when required; internally consistent with linked records. |
| 9 | Negative and counter-evidence | Failures, null-compatible findings, negative cases or alternatives. Validation: non-empty when required; internally consistent with linked records. |
| 10 | Reproduction, audit or adversarial check | Proportionate independent challenge. Validation: non-empty when required; internally consistent with linked records. |
| 11 | Acceptance and narrowing rule | How wording changes. Validation: non-empty when required; internally consistent with linked records. |
| 12 | Owner, reviewer, date and version | Lifecycle record. Validation: explicit version or dated revision; no ambiguous labels such as final-final. |

B19. Evidential Object and Navigation Audit — Full

CSV: companion/04_TEMPLATES_FULL/EVIDENTIAL_OBJECT_NAVIGATION_AUDIT_FULL.csv

Purpose. Audit the semantic and technical integrity of figures, tables, equations, listings and cross-references.

Use and completion. Add one row per inspectable object. Preserve stable identifiers and versions. Every object represents the accepted study and every destination works.

Boundary. controlled project metadata; no credentials, direct identifiers or confidential payloads Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | object_id | Stable identifier for object id. Use a reproducible project naming convention. Validation: non-empty stable identifier; unique within the project namespace. |
| 2 | object_type | Declared evidential or rights-relevant object class used to select the appropriate inspection and handling rule. Validation: non-empty when required; internally consistent with linked records. |
| 3 | caption_or_title | Exact caption or title that identifies the evidential object and states its role without overclaiming. Validation: non-empty when required; internally consistent with linked records. |
| 4 | semantic_test | Test that checks whether caption, labels, body interpretation and claim wording convey the same bounded meaning. Validation: non-empty when required; internally consistent with linked records. |
| 5 | body_interpretation | Meaning conveyed by the surrounding prose when the evidential object is reached; it must agree with the caption, labels and body claim. Validation: non-empty when required; internally consistent with linked records. |
| 6 | claim_boundary | Material constraint, uncertainty or boundary associated with claim boundary. Validation: non-empty when required; internally consistent with linked records. |
| 7 | numbering | Displayed number and sequence relationship for the evidential object, including agreement with all cross-references and lists. Validation: non-empty when required; internally consistent with linked records. |
| 8 | field_or_bookmark | Exact field, cross-reference, bookmark or link target whose existence and destination are being tested. Validation: non-empty when required; internally consistent with linked records. |
| 9 | alt_text_or_header | Alternative text, table-header structure or equivalent navigation aid required to identify and interpret the evidential object. Validation: non-empty when required; internally consistent with linked records. |
| 10 | rights_status | Permission, licence, ownership or unresolved-rights status for the intended use. Controlled values: pending clearance; cleared for declared use; restricted; prohibited; not applicable. Validation: use one exact value from controlled vocabulary: rights_status. |
| 11 | render_status | Current controlled status for render status. Controlled values: not rendered; candidate; passed technical proof; failed; pending Microsoft Word proof. Validation: use one exact value from controlled vocabulary: render_status. |
| 12 | destination_test | Observable test proving that a cross-reference, bookmark or navigation route reaches the intended object. Validation: non-empty when required; internally consistent with linked records. |
| 13 | reviewer | Named person or competent role that inspected the current version. Validation: non-empty when required; internally consistent with linked records. |
| 14 | status | Current lifecycle or decision status. Use the controlled vocabulary declared for the record. Controlled values: draft; candidate; reviewed; accepted locally; superseded; withdrawn. Validation: use one exact value from controlled vocabulary: lifecycle_status. |

B20. Execution, Context and Provenance Record — Full

CSV: companion/04_TEMPLATES_FULL/EXECUTION_PROVENANCE_RECORD_FULL.csv

Purpose. Preserve lineage from starting state to candidate and accepted work.

Use and completion. Add one row per inspectable object. Preserve stable identifiers and versions. A reviewer can reconstruct versions, environment, manual interventions, failures and disposition.

Boundary. record versions and evidence locators, not secrets, personal data or proprietary payloads Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | run_id | Stable identifier for one execution or analysis run. Validation: non-empty stable identifier; unique within the project namespace. |
| 2 | work_unit_id | Stable identifier linking execution to an authorised work-unit brief. Validation: non-empty stable identifier; unique within the project namespace. |
| 3 | source_state | Verified source or identity information for source state, sufficient for independent resolution. Validation: non-empty when required; internally consistent with linked records. |
| 4 | data_or_material_id | Stable identifier for data or material id. Use a reproducible project naming convention. Validation: non-empty stable identifier; unique within the project namespace. |
| 5 | environment | Exact hardware, operating system, software, runtime and material conditions needed to execute or demonstrate the step. Validation: non-empty when required; internally consistent with linked records. |
| 6 | dependencies | Exact software, package, service, data, authority or environmental dependencies required to reproduce the work unit. Validation: non-empty when required; internally consistent with linked records. |
| 7 | action | Specific, owned and testable action for action. Validation: non-empty when required; internally consistent with linked records. |
| 8 | candidate_output | Object produced by the work unit before inspection and disposition. Validation: non-empty when required; internally consistent with linked records. |
| 9 | manual_intervention | Human intervention applied during execution, including its reason, timing and effect on reproducibility. Validation: non-empty when required; internally consistent with linked records. |
| 10 | material_ai_assistance | Consequential generative AI assistance affecting meaning, method, code, evidence, analysis or presentation. Validation: non-empty when required; internally consistent with linked records. |
| 11 | failure_or_deviation | Observed failure, exception or material departure from the authorised plan. Preserve rather than erase it. Validation: non-empty when required; internally consistent with linked records. |
| 12 | inspection | Test, review or comparison used to determine whether the candidate output is acceptable for its declared downstream use. Validation: non-empty when required; internally consistent with linked records. |
| 13 | disposition | Accepted, repaired, repeated, rejected, deferred or quarantined outcome for the candidate object. Controlled values: accept locally; repair; repeat; reject; defer; quarantine. Validation: use one exact value from controlled vocabulary: work_disposition. |
| 14 | evidence_location | Authorised workspace path, repository-relative path or stable identifier from which the evidence can be retrieved. Validation: non-empty when required; internally consistent with linked records. |
| 15 | date | ISO 8601 date on which the action, observation or disposition occurred. Validation: ISO 8601 date (YYYY-MM-DD). |
| 16 | owner | Person responsible for the object or next action. Use a role rather than personal contact data when appropriate. Validation: non-empty when required; internally consistent with linked records. |

B21. Feasibility Sprint Record — Full

CSV: companion/04_TEMPLATES_FULL/FEASIBILITY_SPRINT_RECORD_FULL.csv

Purpose. Test a costly uncertainty through a bounded, safe and evidential action.

Use and completion. Complete only when the current decision requires this record. The sprint produces retained evidence and a defensible continue, narrow, pivot or stop decision.

Boundary. controlled project metadata; no credentials, direct identifiers or confidential payloads Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | Sprint identifier | Stable identifier. Validation: non-empty when required; internally consistent with linked records. |
| 2 | Critical uncertainty | Most costly unresolved assumption. Validation: non-empty when required; internally consistent with linked records. |
| 3 | Why this uncertainty first | Decision consequence and dependency. Validation: non-empty when required; internally consistent with linked records. |
| 4 | Bounded action | Smallest safe test. Validation: non-empty when required; internally consistent with linked records. |
| 5 | Starting state | Version, data, environment or protocol. Validation: non-empty when required; internally consistent with linked records. |
| 6 | Authority and safety | Permissions, privacy and irreversible-action controls. Validation: non-empty when required; internally consistent with linked records. |
| 7 | Evidence to retain | Logs, sample, screenshot, decision trace, output or observation. Validation: non-empty when required; internally consistent with linked records. |
| 8 | Acceptance criterion | Declared before outcome. Validation: non-empty when required; internally consistent with linked records. |
| 9 | Failure criterion | Declared before outcome. Validation: non-empty when required; internally consistent with linked records. |
| 10 | Outcome | Observed result without interpretation inflation. Validation: non-empty when required; internally consistent with linked records. |
| 11 | Decision | Continue, narrow, pivot or stop. Validation: non-empty when required; internally consistent with linked records. |
| 12 | Objects to update | SCOPE, CORPUS, DECIDE or another record. Validation: non-empty when required; internally consistent with linked records. |
| 13 | Gate reopened | Earliest responsible gate. Controlled values: Project Start Pack / opening control; Problem Gate; Evidence Gate; Design Gate; Execution Gate; Claim Gate; Argument Gate; Editorial Gate; Defence Readiness Gate. Validation: use one exact common gate/control name or an explicit justified external authority route where the record permits it. |
| 14 | Owner, reviewer, dates and version | Complete lifecycle. Validation: explicit version or dated revision; no ambiguous labels such as final-final. |

B22. Gate Record — Full

CSV: companion/04_TEMPLATES_FULL/GATE_RECORD_FULL.csv

Purpose. Record a complete gate disposition, including the strongest objection, unresolved authority, conditions and earliest return gate.

Use and completion. Use for every consequential gate decision or when a minimum gate row cannot preserve the review basis. The decision is supported by named authoritative objects, unresolved authority is explicit and the return route is executable.

Boundary. controlled project metadata; no credentials, direct identifiers or confidential payloads Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | gate_id | Stable gate-decision record identifier, distinct from the canonical gate code. Validation: non-empty stable identifier; unique within the project namespace. |
| 2 | gate_name | Canonical gate or opening-control name under which the full gate record is adjudicated. Controlled values: Project Start Pack / opening control; Problem Gate; Evidence Gate; Design Gate; Execution Gate; Claim Gate; Argument Gate; Editorial Gate; Defence Readiness Gate. Validation: use one exact common gate/control name or an explicit justified external authority route where the record permits it. |
| 3 | decision_question | Exact question that the gate or control must answer before progression. Validation: non-empty when required; internally consistent with linked records. |
| 4 | authoritative_objects | Stable identifiers for the complete set of current objects that govern the gate decision. Validation: non-empty when required; internally consistent with linked records. |
| 5 | evidence_status | State of the required evidence: missing, candidate, verified, conditionally accepted or rejected. Controlled values: missing; candidate; verified; accepted conditionally; rejected. Validation: use one exact value from controlled vocabulary: evidence_status. |
| 6 | strongest_objection | Most consequential realistic objection tested in the full adjudication record, not a weak objection selected for convenience. Validation: non-empty when required; internally consistent with linked records. |
| 7 | unresolved_authority | Named authority, permission or rights basis governing unresolved authority. Validation: non-empty when required; internally consistent with linked records. |
| 8 | decision | Explicit disposition selected from the record’s controlled outcomes and justified by named evidence. Controlled values: pass; pass with conditions; repair; return; await authority; stop. Validation: use one exact value from controlled vocabulary: gate_decision. |
| 9 | conditions_or_repairs | Specific, owned and testable action for conditions or repairs. Validation: non-empty when required; internally consistent with linked records. |
| 10 | earliest_return_gate | Earliest gate responsible for the defect. Later-stage repair must not conceal earlier scientific drift. Controlled values: Project Start Pack / opening control; Problem Gate; Evidence Gate; Design Gate; Execution Gate; Claim Gate; Argument Gate; Editorial Gate; Defence Readiness Gate. Validation: use one exact common gate/control name or an explicit justified external authority route where the record permits it. |
| 11 | reviewer | Named person or competent role that inspected the current version. Validation: non-empty when required; internally consistent with linked records. |
| 12 | decision_date | ISO 8601 date associated with decision date. Validation: ISO 8601 date (YYYY-MM-DD). |
| 13 | version | Explicit version identifier for the record or object. Do not rely on file modification time. Validation: explicit version or dated revision; no ambiguous labels such as final-final. |
| 14 | supersedes | Stable identifier of the earlier gate decision or record replaced by the current version. Validation: non-empty when required; internally consistent with linked records. |
| 15 | status | Current lifecycle or decision status. Use the controlled vocabulary declared for the record. Controlled values: draft; candidate; reviewed; accepted locally; superseded; withdrawn. Validation: use one exact value from controlled vocabulary: lifecycle_status. |

B23. Milestone Evidence Register — Full

CSV: companion/04_TEMPLATES_FULL/MILESTONE_EVIDENCE_REGISTER_FULL.csv

Purpose. Map each milestone or gate to its required scientific, administrative or release record, current version, retained proof and missing-condition response.

Use and completion. Use when several records, authorities or dates must be controlled across the project lifecycle. Every milestone has an owner, accepted version, retained evidence, storage boundary and explicit response to missing or stale objects.

Boundary. controlled project metadata; no credentials, direct identifiers or confidential payloads Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | milestone_id | Stable identifier for milestone id. Use a reproducible project naming convention. Validation: non-empty stable identifier; unique within the project namespace. |
| 2 | milestone_or_gate | Named milestone, opening control or gate at which the record becomes required or is reviewed. Validation: non-empty when required; internally consistent with linked records. |
| 3 | required_record | Exact record or evidence object required at the named milestone or gate. Validation: non-empty when required; internally consistent with linked records. |
| 4 | record_class | Declared class of milestone evidence: scientific project record, administrative dossier item or release record. Validation: non-empty when required; internally consistent with linked records. |
| 5 | authority_or_reviewer | Named authority, permission or rights basis governing authority or reviewer. Validation: non-empty when required; internally consistent with linked records. |
| 6 | version | Explicit version identifier for the record or object. Do not rely on file modification time. Validation: explicit version or dated revision; no ambiguous labels such as final-final. |
| 7 | retained_evidence | Named, retrievable evidence relevant to retained evidence; use a safe locator rather than confidential payload. Validation: non-empty when required; internally consistent with linked records. |
| 8 | storage_boundary | Material constraint, uncertainty or boundary associated with storage boundary. Validation: non-empty when required; internally consistent with linked records. |
| 9 | missing_or_stale_condition | Observable absence, outdated state or unresolved discrepancy that makes the required record unfit for progression. Validation: non-empty when required; internally consistent with linked records. |
| 10 | control_response | Specific action, hold, repair or escalation that controls the missing or stale milestone record. Validation: non-empty when required; internally consistent with linked records. |
| 11 | owner | Person responsible for the object or next action. Use a role rather than personal contact data when appropriate. Validation: non-empty when required; internally consistent with linked records. |
| 12 | due_date | ISO 8601 date associated with due date. Validation: ISO 8601 date (YYYY-MM-DD). |
| 13 | status | Current lifecycle or decision status. Use the controlled vocabulary declared for the record. Controlled values: draft; candidate; reviewed; accepted locally; superseded; withdrawn. Validation: use one exact value from controlled vocabulary: lifecycle_status. |

B24. Mock Defence And Recovery Record — Full

CSV: companion/04_TEMPLATES_FULL/MOCK_DEFENCE_AND_RECOVERY_RECORD_FULL.csv

Purpose. Record unseen-question, evidence-retrieval, failure, fallback and incident tests and the recovery action they require.

Use and completion. Use for independent rehearsals and any retest after a blocking defence defect. The tested person can retrieve evidence, state limits, recover safely and identify the earliest gate responsible for failure.

Boundary. may reference restricted administrative objects; store only safe identifiers and segregated locators Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | test_id | Stable identifier for one test, rehearsal or challenge. Validation: non-empty stable identifier; unique within the project namespace. |
| 2 | test_type | Declared rehearsal or challenge type used to expose a technical, evidential, timing, ownership or defence failure. Validation: non-empty when required; internally consistent with linked records. |
| 3 | scenario_or_question | Exact question represented by scenario or question. Validation: non-empty when required; internally consistent with linked records. |
| 4 | expected_evidence_path | Named, retrievable evidence relevant to expected evidence path; use a safe locator rather than confidential payload. Validation: non-empty when required; internally consistent with linked records. |
| 5 | observed_response | Observed result for observed response, recorded without inflating interpretation. Validation: non-empty when required; internally consistent with linked records. |
| 6 | failure_or_delay | Observed rehearsal failure or delay, including the affected scientific object and the point at which recovery began. Validation: non-empty when required; internally consistent with linked records. |
| 7 | recovery_action | Specific, owned and testable action for recovery action. Validation: non-empty when required; internally consistent with linked records. |
| 8 | fallback_used | Whether the rehearsed fallback was invoked and, when it was, which exact accepted fallback state was used. Validation: non-empty when required; internally consistent with linked records. |
| 9 | scientific_identity_preserved | Whether recovery preserved the same accepted release, evidence body, route and claim boundary rather than substituting a new project state. Validation: non-empty when required; internally consistent with linked records. |
| 10 | earliest_return_gate | Earliest gate responsible for the defect. Later-stage repair must not conceal earlier scientific drift. Controlled values: Project Start Pack / opening control; Problem Gate; Evidence Gate; Design Gate; Execution Gate; Claim Gate; Argument Gate; Editorial Gate; Defence Readiness Gate. Validation: use one exact common gate/control name or an explicit justified external authority route where the record permits it. |
| 11 | reviewer | Named person or competent role that inspected the current version. Validation: non-empty when required; internally consistent with linked records. |
| 12 | date | ISO 8601 date on which the action, observation or disposition occurred. Validation: ISO 8601 date (YYYY-MM-DD). |
| 13 | status | Current lifecycle or decision status. Use the controlled vocabulary declared for the record. Controlled values: draft; candidate; reviewed; accepted locally; superseded; withdrawn. Validation: use one exact value from controlled vocabulary: lifecycle_status. |

B25. Package Consistency Record — Full

CSV: companion/04_TEMPLATES_FULL/PACKAGE_CONSISTENCY_RECORD_FULL.csv

Purpose. Test scientific-content identity across the authoritative source, official artefacts, evidence package, slides, demonstration and public-release candidate.

Use and completion. Use before submission freeze, examination-copy production, defence rehearsal or external release. No interface changes the question, corpus, release, result, uncertainty, conclusion, rights or disclosure state.

Boundary. may reference restricted administrative objects; store only safe identifiers and segregated locators Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | interface_id | Stable identifier for interface id. Use a reproducible project naming convention. Validation: non-empty stable identifier; unique within the project namespace. |
| 2 | interface | Exact boundary between two package objects, versions, representations or submission components whose consistency is tested. Validation: non-empty when required; internally consistent with linked records. |
| 3 | authoritative_source | Verified source or identity information for authoritative source, sufficient for independent resolution. Validation: non-empty when required; internally consistent with linked records. |
| 4 | version | Explicit version identifier for the record or object. Do not rely on file modification time. Validation: explicit version or dated revision; no ambiguous labels such as final-final. |
| 5 | hash_or_identifier | Cryptographic digest or controlled identifier for hash or identifier. Validation: non-empty when required; internally consistent with linked records. |
| 6 | scientific_identity_test | Test proving that two package representations or recovery paths refer to the same accepted scientific object and claim state. Validation: non-empty when required; internally consistent with linked records. |
| 7 | rights_status | Permission, licence, ownership or unresolved-rights status for the intended use. Controlled values: pending clearance; cleared for declared use; restricted; prohibited; not applicable. Validation: use one exact value from controlled vocabulary: rights_status. |
| 8 | privacy_status | Public, internal, confidential, restricted or mixed access state after review. Controlled values: public; internal; confidential; restricted; mixed. Validation: use one exact value from controlled vocabulary: privacy_class. |
| 9 | mismatch | Exact inconsistency between package representations, versions, metadata, claims, figures, tables or submission fields. Validation: non-empty when required; internally consistent with linked records. |
| 10 | repair | Specific, owned and testable action for repair. Validation: non-empty when required; internally consistent with linked records. |
| 11 | retest_evidence | Named, retrievable evidence relevant to retest evidence; use a safe locator rather than confidential payload. Validation: non-empty when required; internally consistent with linked records. |
| 12 | reviewer | Named person or competent role that inspected the current version. Validation: non-empty when required; internally consistent with linked records. |
| 13 | date | ISO 8601 date on which the action, observation or disposition occurred. Validation: ISO 8601 date (YYYY-MM-DD). |
| 14 | status | Current lifecycle or decision status. Use the controlled vocabulary declared for the record. Controlled values: draft; candidate; reviewed; accepted locally; superseded; withdrawn. Validation: use one exact value from controlled vocabulary: lifecycle_status. |

B26. Presentation Spine Record — Full

CSV: companion/04_TEMPLATES_FULL/PRESENTATION_SPINE_RECORD_FULL.csv

Purpose. Compress the accepted argument into a timed, accessible and claim-bounded presentation without restoring rejected wording.

Use and completion. Use when building or revising the defence presentation. Every block has a purpose, evidence anchor, boundary, source location, time budget and rehearsal result.

Boundary. controlled project metadata; no credentials, direct identifiers or confidential payloads Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | slide_or_block | Exact presentation slide, demonstration block or defence segment represented by the row. Validation: non-empty when required; internally consistent with linked records. |
| 2 | purpose | Decision, claim, evidence obligation or reader task served by the step, record, slide or demonstration action. Validation: non-empty when required; internally consistent with linked records. |
| 3 | claim_or_question | Exact question represented by claim or question. Validation: non-empty when required; internally consistent with linked records. |
| 4 | decisive_evidence | Named, retrievable evidence relevant to decisive evidence; use a safe locator rather than confidential payload. Validation: non-empty when required; internally consistent with linked records. |
| 5 | boundary | Explicit scope limit for population, case, corpus, time, environment, method or transfer. Validation: non-empty when required; internally consistent with linked records. |
| 6 | visual_object | Figure, table, screenshot, diagram, code extract or other visual object used in the presentation block. Validation: non-empty when required; internally consistent with linked records. |
| 7 | source_location | Verified source or identity information for source location, sufficient for independent resolution. Validation: non-empty when required; internally consistent with linked records. |
| 8 | time_budget | Maximum presentation or demonstration time allocated to the block, including transition and recovery allowance. Validation: non-empty when required; internally consistent with linked records. |
| 9 | accessibility_check | Declared accessibility check for the slide, block or visual object, with an observable pass condition rather than an unsupported assertion. Validation: non-empty when required; internally consistent with linked records. |
| 10 | prohibited_overclaim | Exact bounded claim or claim-related role represented by prohibited overclaim. Validation: non-empty when required; internally consistent with linked records. |
| 11 | rehearsal_result | Observed result for rehearsal result, recorded without inflating interpretation. Controlled values: pass; pass with conditions; repair; return. Validation: use one exact value from controlled vocabulary: rehearsal_result. |
| 12 | status | Current lifecycle or decision status. Use the controlled vocabulary declared for the record. Controlled values: draft; candidate; reviewed; accepted locally; superseded; withdrawn. Validation: use one exact value from controlled vocabulary: lifecycle_status. |

B27. Project Start Pack — Full

CSV: companion/04_TEMPLATES_FULL/PROJECT_START_PACK_FULL.csv

Purpose. Establish the product, route, access, authority, workspace and first controlled deliverable.

Use and completion. Complete only when the current decision requires this record. A reviewer can identify the project, inspect access and risk, then authorise one bounded next action.

Boundary. controlled project metadata; no credentials, direct identifiers or confidential payloads Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | Project identifier | Stable identifier. Validation: non-empty when required; internally consistent with linked records. |
| 2 | Assessed product | Exact product type. Validation: non-empty when required; internally consistent with linked records. |
| 3 | Working title | Current recorded title. Validation: non-empty when required; internally consistent with linked records. |
| 4 | Observed situation | Evidence-based context. Validation: non-empty when required; internally consistent with linked records. |
| 5 | Problem | Consequential and bounded problem. Validation: non-empty when required; internally consistent with linked records. |
| 6 | Provisional route | Dominant and secondary route. Controlled values: build-and-evaluate; algorithmic or simulation study; predictive or machine-learning study; quantitative empirical study; qualitative inquiry; case study; formal evidence synthesis; hybrid route. Validation: use one exact value from controlled vocabulary: route. |
| 7 | Research object | Artefact, population, case, corpus, process or study set. Validation: non-empty when required; internally consistent with linked records. |
| 8 | Access status | Data, participants, systems, documents, compute and sources. Controlled values: pending verification; available; available with conditions; restricted; unavailable; not applicable. Validation: use one exact value from controlled vocabulary: access_status. |
| 9 | Authority map | Advice, academic approval, ethics, data owner, security and licence authority. Validation: non-empty when required; internally consistent with linked records. |
| 10 | Confidentiality class | Public, internal, confidential, restricted or mixed. Controlled values: public; internal; confidential; restricted; mixed. Validation: use one exact value from controlled vocabulary: privacy_class. |
| 11 | Feasibility risks | Time, skills, compute, recruitment, access, licence and evaluation burden. Validation: non-empty when required; internally consistent with linked records. |
| 12 | Workspace root | Authoritative working location; do not record credentials. Validation: non-empty when required; internally consistent with linked records. |
| 13 | First deliverable | One bounded inspectable object. Validation: non-empty when required; internally consistent with linked records. |
| 14 | Owner | Responsible student. Validation: non-empty when required; internally consistent with linked records. |
| 15 | Reviewer decision | Proceed, proceed with actions, repair or stop. Validation: non-empty when required; internally consistent with linked records. |
| 16 | Version, date and next review | Stable version record. Validation: explicit version or dated revision; no ambiguous labels such as final-final. |

B28. Risk and Assumption Register — Full

CSV: companion/04_TEMPLATES_FULL/RISK_ASSUMPTION_REGISTER_FULL.csv

Purpose. Make consequential assumptions, risks, mitigations and reopening triggers inspectable.

Use and completion. Add one row per inspectable object. Preserve stable identifiers and versions. Every high-impact item has an owner, test or mitigation and a decision consequence.

Boundary. controlled project metadata; no credentials, direct identifiers or confidential payloads Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | item_id | Stable identifier for item id. Use a reproducible project naming convention. Validation: non-empty stable identifier; unique within the project namespace. |
| 2 | type | Controlled category of risk, assumption, dependency or uncertainty represented by the row. Validation: non-empty when required; internally consistent with linked records. |
| 3 | statement | Exact risk, assumption or dependency statement that can be challenged and tested. Validation: non-empty when required; internally consistent with linked records. |
| 4 | basis | Named evidence, assumption, authority or reasoning basis supporting the risk or decision statement. Validation: non-empty when required; internally consistent with linked records. |
| 5 | likelihood_or_uncertainty | Material constraint, uncertainty or boundary associated with likelihood or uncertainty. Validation: non-empty when required; internally consistent with linked records. |
| 6 | impact | Material effect on validity, feasibility, safety, rights, schedule or claim wording if the risk or assumption fails. Validation: non-empty when required; internally consistent with linked records. |
| 7 | mitigation_or_test | Specific, owned and testable action for mitigation or test. Validation: non-empty when required; internally consistent with linked records. |
| 8 | owner | Person responsible for the object or next action. Use a role rather than personal contact data when appropriate. Validation: non-empty when required; internally consistent with linked records. |
| 9 | trigger | Observable event or threshold that activates the risk response, review or reopening decision. Validation: non-empty when required; internally consistent with linked records. |
| 10 | decision_consequence | Required consequence of the risk or assumption result: continue, narrow, pivot or stop. Controlled values: continue; narrow; pivot; stop. Validation: non-empty when required; internally consistent with linked records. |
| 11 | status | Current lifecycle or decision status. Use the controlled vocabulary declared for the record. Controlled values: draft; candidate; reviewed; accepted locally; superseded; withdrawn. Validation: use one exact value from controlled vocabulary: lifecycle_status. |
| 12 | version | Explicit version identifier for the record or object. Do not rely on file modification time. Validation: explicit version or dated revision; no ambiguous labels such as final-final. |

B29. Route Selector — Full

CSV: companion/04_TEMPLATES_FULL/ROUTE_SELECTOR_FULL.csv

Purpose. Select a dominant route through evidence obligations rather than topic vocabulary.

Use and completion. Complete only when the current decision requires this record. The route, unit, comparison, evidence body, uncertainty and forbidden inference are mutually compatible.

Boundary. controlled project metadata; no credentials, direct identifiers or confidential payloads Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | Assessed product | Project, bachelor’s thesis, master’s dissertation or formal evidence synthesis. Validation: non-empty when required; internally consistent with linked records. |
| 2 | Working title | Use the exact current title. Validation: non-empty when required; internally consistent with linked records. |
| 3 | Problem object | Name the artefact, population, process, case, corpus or study set. Validation: non-empty when required; internally consistent with linked records. |
| 4 | Dominant route | Select one of the eight locked routes. Controlled values: build-and-evaluate; algorithmic or simulation study; predictive or machine-learning study; quantitative empirical study; qualitative inquiry; case study; formal evidence synthesis; hybrid route. Validation: use one exact value from controlled vocabulary: route. |
| 5 | Secondary component | Name only if it produces distinct evidence. Validation: non-empty when required; internally consistent with linked records. |
| 6 | Integration point | Required for a hybrid route. Validation: non-empty when required; internally consistent with linked records. |
| 7 | Unit of analysis | Name the unit on which observations or interpretations are made. Validation: non-empty when required; internally consistent with linked records. |
| 8 | Primary question form | Write the route-appropriate question. Validation: non-empty when required; internally consistent with linked records. |
| 9 | Core evidence body | Name all evidence required for the principal claim. Validation: non-empty when required; internally consistent with linked records. |
| 10 | Credible comparison or reference | Baseline, reference case, alternative explanation or protocol basis. Validation: non-empty when required; internally consistent with linked records. |
| 11 | Principal uncertainty | Sampling, model, measurement, interpretive, numerical or transfer uncertainty. Validation: non-empty when required; internally consistent with linked records. |
| 12 | Forbidden inference | Name the attractive claim not authorised by the design. Validation: non-empty when required; internally consistent with linked records. |
| 13 | Current gate | Name the gate currently being prepared. Controlled values: Project Start Pack / opening control; Problem Gate; Evidence Gate; Design Gate; Execution Gate; Claim Gate; Argument Gate; Editorial Gate; Defence Readiness Gate. Validation: use one exact common gate/control name or an explicit justified external authority route where the record permits it. |
| 14 | Next record | Name the next record and owner. Validation: non-empty when required; internally consistent with linked records. |

B30. SCOPE Canvas — Full

CSV: companion/04_TEMPLATES_FULL/SCOPE_CANVAS_FULL.csv

Purpose. Externalise scope, evidence, boundaries and uncertainty before commitment.

Use and completion. Complete only when the current decision requires this record. The question, route, evidence, contribution and reopening triggers form a coherent contract.

Boundary. controlled project metadata; no credentials, direct identifiers or confidential payloads Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | Situation | Observed context and evidence basis. Validation: non-empty when required; internally consistent with linked records. |
| 2 | Concern | Consequential problem or knowledge gap. Validation: non-empty when required; internally consistent with linked records. |
| 3 | Object | Artefact, population, corpus, process or case. Validation: non-empty when required; internally consistent with linked records. |
| 4 | Purpose | Build, test, compare, estimate, interpret, investigate or synthesise. Validation: non-empty when required; internally consistent with linked records. |
| 5 | Evidence obligation | Evidence required for the answer. Validation: non-empty when required; internally consistent with linked records. |
| 6 | Boundary | Time, environment, population, case, corpus and exclusions. Validation: non-empty when required; internally consistent with linked records. |
| 7 | Contribution | Smallest defensible contribution. Validation: non-empty when required; internally consistent with linked records. |
| 8 | Research question | Single route-aligned question. Validation: non-empty when required; internally consistent with linked records. |
| 9 | Alternative question rejected | State why it was rejected. Validation: non-empty when required; internally consistent with linked records. |
| 10 | Assumptions | Assumptions not yet established. Validation: non-empty when required; internally consistent with linked records. |
| 11 | Known uncertainty | What is unknown at scoping time. Validation: non-empty when required; internally consistent with linked records. |
| 12 | Access evidence | Permission, availability or feasibility evidence. Validation: non-empty when required; internally consistent with linked records. |
| 13 | Reopening trigger | Finding that forces narrowing, pivoting or stopping. Validation: non-empty when required; internally consistent with linked records. |
| 14 | Reviewer decision and version | Decision, reviewer, date and version. Validation: explicit version or dated revision; no ambiguous labels such as final-final. |

B31. Search Strategy Record — Full

CSV: companion/04_TEMPLATES_FULL/SEARCH_STRATEGY_RECORD_FULL.csv

Purpose. Make discovery routes, dates, strings and limits inspectable.

Use and completion. Add one row per inspectable object. Preserve stable identifiers and versions. A third party can reconstruct the search sufficiently to understand the corpus boundary.

Boundary. bibliographic and source metadata only; do not redistribute restricted full texts Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | search_id | Stable identifier for search id. Use a reproducible project naming convention. Validation: non-empty stable identifier; unique within the project namespace. |
| 2 | question_or_concept | Exact question represented by question or concept. Validation: non-empty when required; internally consistent with linked records. |
| 3 | source_or_database | Verified source or identity information for source or database, sufficient for independent resolution. Validation: non-empty when required; internally consistent with linked records. |
| 4 | exact_query_or_route | Reproducible search expression, browsing route, API request or retrieval procedure used for the source set. Validation: non-empty when required; internally consistent with linked records. |
| 5 | filters | Explicit filters, limits and exclusions applied during search or retrieval, including defaults that could affect coverage. Validation: non-empty when required; internally consistent with linked records. |
| 6 | date_run | ISO 8601 date associated with date run. Validation: ISO 8601 date (YYYY-MM-DD). |
| 7 | coverage_window | Exact dates, versions, populations, repositories or other bounds within which the search or retrieval was performed. Validation: non-empty when required; internally consistent with linked records. |
| 8 | result_count | Observed result for result count, recorded without inflating interpretation. Validation: non-empty when required; internally consistent with linked records. |
| 9 | export_or_capture | Controlled export, screenshot, log or other retained artefact that preserves the search or retrieval state. Validation: non-empty when required; internally consistent with linked records. |
| 10 | limitations | Material constraint, uncertainty or boundary associated with limitations. Validation: non-empty when required; internally consistent with linked records. |
| 11 | owner | Person responsible for the object or next action. Use a role rather than personal contact data when appropriate. Validation: non-empty when required; internally consistent with linked records. |
| 12 | version | Explicit version identifier for the record or object. Do not rely on file modification time. Validation: explicit version or dated revision; no ambiguous labels such as final-final. |

B32. Section Contract Register — Full

CSV: companion/04_TEMPLATES_FULL/SECTION_CONTRACT_REGISTER_FULL.csv

Purpose. Assign each manuscript section an intellectual function, evidence set and boundary.

Use and completion. Add one row per inspectable object. Preserve stable identifiers and versions. No section exists only because a conventional heading was expected.

Boundary. controlled project metadata; no credentials, direct identifiers or confidential payloads Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | section_id | Stable identifier for section id. Use a reproducible project naming convention. Validation: non-empty stable identifier; unique within the project namespace. |
| 2 | section_title | Exact current section heading linked to its contract, promise, reasoning move and handoff. Validation: non-empty when required; internally consistent with linked records. |
| 3 | promise | Specific question, claim or reader expectation that the section undertakes to satisfy. Validation: non-empty when required; internally consistent with linked records. |
| 4 | evidence_set | Named, retrievable evidence relevant to evidence set; use a safe locator rather than confidential payload. Validation: non-empty when required; internally consistent with linked records. |
| 5 | reasoning_move | Logical operation performed by the section, such as defining, comparing, testing, interpreting, limiting or synthesising. Validation: non-empty when required; internally consistent with linked records. |
| 6 | boundary | Explicit scope limit for population, case, corpus, time, environment, method or transfer. Validation: non-empty when required; internally consistent with linked records. |
| 7 | handoff | Explicit transition from the section’s accepted output to the next section, gate or controlled record. Validation: non-empty when required; internally consistent with linked records. |
| 8 | claims_served | Exact bounded claim or claim-related role represented by claims served. Validation: non-empty when required; internally consistent with linked records. |
| 9 | objects_or_figures | Named tables, figures, listings, records or other objects that the section must introduce, interpret and hand forward. Validation: non-empty when required; internally consistent with linked records. |
| 10 | status | Current lifecycle or decision status. Use the controlled vocabulary declared for the record. Controlled values: draft; candidate; reviewed; accepted locally; superseded; withdrawn. Validation: use one exact value from controlled vocabulary: lifecycle_status. |
| 11 | reviewer | Named person or competent role that inspected the current version. Validation: non-empty when required; internally consistent with linked records. |
| 12 | version | Explicit version identifier for the record or object. Do not rely on file modification time. Validation: explicit version or dated revision; no ambiguous labels such as final-final. |

B33. Similarity, AI and Authorship Record — Full

CSV: companion/04_TEMPLATES_FULL/SIMILARITY_AI_AUTHORSHIP_RECORD_FULL.csv

Purpose. Separate similarity, attribution, text recycling, AI disclosure and oral ownership.

Use and completion. Complete only when the current decision requires this record. No detector or score is used as a substitute for source verification or authorship responsibility.

Boundary. do not paste confidential prompts, participant data, credentials or restricted source content Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | Review context | Institutional or publisher requirement. Validation: non-empty when required; internally consistent with linked records. |
| 2 | Similarity report | Tool, date, version and scope. Validation: non-empty when required; internally consistent with linked records. |
| 3 | Flagged overlap reviewed | Legitimate quotation, common phrasing, recycling or problem. Validation: non-empty when required; internally consistent with linked records. |
| 4 | Attribution action | Correction or justification. Validation: non-empty when required; internally consistent with linked records. |
| 5 | Material AI uses | TRACE identifiers. Validation: non-empty when required; internally consistent with linked records. |
| 6 | Disclosure mapping | Required declaration or manuscript statement. Validation: non-empty when required; internally consistent with linked records. |
| 7 | Confidentiality check | No prohibited inputs. Validation: non-empty when required; internally consistent with linked records. |
| 8 | Independent verification | Sources, tests or primary artefacts. Validation: non-empty when required; internally consistent with linked records. |
| 9 | Student semantic decisions | Meaning-changing choices retained by student. Validation: non-empty when required; internally consistent with linked records. |
| 10 | Oral ownership test | Can explain sources, method, results and limits. Validation: non-empty when required; internally consistent with linked records. |
| 11 | Reviewer decision | Pass, repair or return. Validation: non-empty when required; internally consistent with linked records. |
| 12 | Version and date | Lifecycle record. Validation: ISO 8601 date (YYYY-MM-DD). |

B34. Source, Rights and Attribution Record — Full

CSV: companion/04_TEMPLATES_FULL/SOURCE_RIGHTS_ATTRIBUTION_RECORD_FULL.csv

Purpose. Verify source identity, claim fitness, attribution and rights bidirectionally.

Use and completion. Add one row per inspectable object. Preserve stable identifiers and versions. Every load-bearing source and reused object has a defensible identity, use and rights status.

Boundary. bibliographic and source metadata only; do not redistribute restricted full texts Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | object_id | Stable identifier for object id. Use a reproducible project naming convention. Validation: non-empty stable identifier; unique within the project namespace. |
| 2 | object_type | Declared evidential or rights-relevant object class used to select the appropriate inspection and handling rule. Validation: non-empty when required; internally consistent with linked records. |
| 3 | verified_identity | Resolved creator, owner, source, work or asset identity supporting attribution and rights assessment. Validation: non-empty when required; internally consistent with linked records. |
| 4 | official_or_original_source | Verified source or identity information for official or original source, sufficient for independent resolution. Validation: non-empty when required; internally consistent with linked records. |
| 5 | claim_or_use | Exact bounded claim or claim-related role represented by claim or use. Validation: non-empty when required; internally consistent with linked records. |
| 6 | claim_fitness | Exact bounded claim or claim-related role represented by claim fitness. Validation: non-empty when required; internally consistent with linked records. |
| 7 | attribution_required | Exact credit, citation, notice or acknowledgement required by the verified rights basis for the intended use. Validation: non-empty when required; internally consistent with linked records. |
| 8 | rights_basis | Named authority, permission or rights basis governing rights basis. Validation: non-empty when required; internally consistent with linked records. |
| 9 | permission_or_licence | Named authority, permission or rights basis governing permission or licence. Validation: non-empty when required; internally consistent with linked records. |
| 10 | restriction | Verified licence, privacy, confidentiality, contractual, institutional or technical restriction on the intended use. Validation: non-empty when required; internally consistent with linked records. |
| 11 | verification_date | ISO 8601 date associated with verification date. Validation: ISO 8601 date (YYYY-MM-DD). |
| 12 | reviewer | Named person or competent role that inspected the current version. Validation: non-empty when required; internally consistent with linked records. |
| 13 | status | Current lifecycle or decision status. Use the controlled vocabulary declared for the record. Controlled values: draft; candidate; reviewed; accepted locally; superseded; withdrawn. Validation: use one exact value from controlled vocabulary: lifecycle_status. |

B35. Submission Package Manifest — Full

CSV: companion/04_TEMPLATES_FULL/SUBMISSION_PACKAGE_MANIFEST_FULL.csv

Purpose. Separate institutional submission objects, private evidence and unpublished release candidates.

Use and completion. Add one row per inspectable object. Preserve stable identifiers and versions. Every file has a role, version, hash, rights status and destination; no private object is published accidentally.

Boundary. may reference restricted administrative objects; store only safe identifiers and segregated locators Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | package_item_id | Stable identifier for package item id. Use a reproducible project naming convention. Validation: non-empty stable identifier; unique within the project namespace. |
| 2 | filename | Exact filename of the controlled package object, including extension and approved naming convention. Validation: non-empty when required; internally consistent with linked records. |
| 3 | object_class | Declared package-object class, such as manuscript, figure, table, form, evidence capture or metadata record. Validation: non-empty when required; internally consistent with linked records. |
| 4 | required_by | Named gate, authority, regulation, publisher instruction or package rule that makes the object necessary. Validation: non-empty when required; internally consistent with linked records. |
| 5 | version | Explicit version identifier for the record or object. Do not rely on file modification time. Validation: explicit version or dated revision; no ambiguous labels such as final-final. |
| 6 | sha256 | Lowercase SHA-256 digest of the exact controlled file. Validation: 64 lowercase hexadecimal characters where a file digest applies. |
| 7 | content_identity | Stable content state, version, checksum or other identifier proving which exact object is intended for the package. Validation: non-empty when required; internally consistent with linked records. |
| 8 | rights_status | Permission, licence, ownership or unresolved-rights status for the intended use. Controlled values: pending clearance; cleared for declared use; restricted; prohibited; not applicable. Validation: use one exact value from controlled vocabulary: rights_status. |
| 9 | privacy_status | Public, internal, confidential, restricted or mixed access state after review. Controlled values: public; internal; confidential; restricted; mixed. Validation: use one exact value from controlled vocabulary: privacy_class. |
| 10 | destination | Exact package location, portal field or controlled folder in which the object must be placed. Validation: non-empty when required; internally consistent with linked records. |
| 11 | submission_status | Current controlled status for submission status. Controlled values: not assembled; assembled; internally reviewed; authorised for submission; submitted with retained evidence; superseded. Validation: use one exact value from controlled vocabulary: submission_status. |
| 12 | notes | Optional concise qualification that cannot be represented elsewhere; do not use it for unstructured personal or confidential payloads. Validation: non-empty when required; internally consistent with linked records. |

B36. Synthesis Memo — Full

CSV: companion/04_TEMPLATES_FULL/SYNTHESIS_MEMO_FULL.csv

Purpose. Convert source notes into a bounded pattern, contradiction or uncertainty.

Use and completion. Complete only when the current decision requires this record. The memo states the evidence base, synthesis logic, counter-evidence and consequence for the project.

Boundary. bibliographic and source metadata only; do not redistribute restricted full texts Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | Memo identifier | Stable identifier. Validation: non-empty when required; internally consistent with linked records. |
| 2 | Question or decision | What the synthesis informs. Validation: non-empty when required; internally consistent with linked records. |
| 3 | Included source/study set | Stable IDs. Validation: non-empty when required; internally consistent with linked records. |
| 4 | Identity resolution | Publication-to-study mapping where relevant. Validation: non-empty when required; internally consistent with linked records. |
| 5 | Synthesis method | Narrative, thematic, tabular, quantitative or other declared method. Validation: non-empty when required; internally consistent with linked records. |
| 6 | Pattern | Supported convergence. Validation: non-empty when required; internally consistent with linked records. |
| 7 | Contradiction | Disagreement or incompatible result. Validation: non-empty when required; internally consistent with linked records. |
| 8 | Uncertainty | Missing, weak or indirect evidence. Validation: non-empty when required; internally consistent with linked records. |
| 9 | Gap wording | Bounded finding, not a universal absence claim. Validation: non-empty when required; internally consistent with linked records. |
| 10 | Project consequence | Proceed, revise question, change design or suspend claim. Validation: non-empty when required; internally consistent with linked records. |
| 11 | Claim boundary | What the memo cannot support. Validation: non-empty when required; internally consistent with linked records. |
| 12 | Reviewer, date and version | Lifecycle record. Validation: explicit version or dated revision; no ambiguous labels such as final-final. |

B37. TRACE Record — Full

CSV: companion/04_TEMPLATES_FULL/TRACE_RECORD_FULL.csv

Purpose. Record consequential AI use from task to verification, disposition and disclosure.

Use and completion. Add one row per inspectable object. Preserve stable identifiers and versions. No AI output is treated as evidence or authority and the student retains semantic responsibility.

Boundary. do not paste confidential prompts, participant data, credentials or restricted source content Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | use_id | Stable identifier for one consequential generative AI use event. Validation: non-empty stable identifier; unique within the project namespace. |
| 2 | project_object | Exact project object whose production, interpretation or acceptance was materially affected by generative AI use. Validation: non-empty when required; internally consistent with linked records. |
| 3 | task | Exact consequential task delegated to or assisted by the generative system. Validation: non-empty when required; internally consistent with linked records. |
| 4 | tool_provider | Named provider or responsible organisation for the generative tool, recorded without implying endorsement or current approval. Validation: non-empty when required; internally consistent with linked records. |
| 5 | tool_or_model_version | Exact tool, model or build version where available. Do not infer an unverified version. Validation: explicit version or dated revision; no ambiguous labels such as final-final. |
| 6 | date | ISO 8601 date on which the action, observation or disposition occurred. Validation: ISO 8601 date (YYYY-MM-DD). |
| 7 | context_supplied | Context supplied to the generative system, excluding unnecessary personal, confidential or rights-restricted material. Validation: non-empty when required; internally consistent with linked records. |
| 8 | confidentiality_class | Public, internal, confidential, restricted or mixed classification for the project object after privacy and authority review. Controlled values: public; internal; confidential; restricted; mixed. Validation: use one exact value from controlled vocabulary: privacy_class. |
| 9 | candidate_output | Object produced by the work unit before inspection and disposition. Validation: non-empty when required; internally consistent with linked records. |
| 10 | material_risk | Material constraint, uncertainty or boundary associated with material risk. Validation: non-empty when required; internally consistent with linked records. |
| 11 | independent_verification | Source, test, primary artefact or competent review path independent of the generating tool output. Validation: non-empty when required; internally consistent with linked records. |
| 12 | student_decision | Human disposition and rationale for accepting, modifying or rejecting candidate assistance. Controlled values: accepted; modified; rejected. Validation: use one exact value from controlled vocabulary: ai_disposition. |
| 13 | effect_on_evidence_reasoning_or_wording | Named, retrievable evidence relevant to effect on evidence reasoning or wording; use a safe locator rather than confidential payload. Validation: non-empty when required; internally consistent with linked records. |
| 14 | disclosure_mapping | Location and wording class of the disclosure required for the consequential AI use, if disclosure is required. Validation: non-empty when required; internally consistent with linked records. |
| 15 | owner | Person responsible for the object or next action. Use a role rather than personal contact data when appropriate. Validation: non-empty when required; internally consistent with linked records. |
| 16 | reviewer | Named person or competent role that inspected the current version. Validation: non-empty when required; internally consistent with linked records. |
| 17 | status | Current lifecycle or decision status. Use the controlled vocabulary declared for the record. Controlled values: draft; candidate; reviewed; accepted locally; superseded; withdrawn. Validation: use one exact value from controlled vocabulary: lifecycle_status. |

B38. Uncertainty and Counter-Evidence Record — Full

CSV: companion/04_TEMPLATES_FULL/UNCERTAINTY_COUNTER_EVIDENCE_RECORD_FULL.csv

Purpose. Preserve uncertainty and evidence that resists the preferred interpretation.

Use and completion. Add one row per inspectable object. Preserve stable identifiers and versions. Negative, null-compatible, inconclusive and invalid results are distinguished and have a disposition.

Boundary. controlled project metadata; no credentials, direct identifiers or confidential payloads Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | item_id | Stable identifier for item id. Use a reproducible project naming convention. Validation: non-empty stable identifier; unique within the project namespace. |
| 2 | claim_id | Stable identifier for one exact claim wording. Validation: non-empty stable identifier; unique within the project namespace. |
| 3 | item_type | Controlled class of uncertainty, counter-evidence item or alternative explanation represented by the row. Validation: non-empty when required; internally consistent with linked records. |
| 4 | evidence_object | Stable identifier or safe locator for the evidence used. Do not paste confidential payloads. Validation: non-empty when required; internally consistent with linked records. |
| 5 | description | Precise description of the uncertainty, counter-evidence item or alternative explanation, separated from its consequence. Validation: non-empty when required; internally consistent with linked records. |
| 6 | source_or_method | Verified source or identity information for source or method, sufficient for independent resolution. Validation: non-empty when required; internally consistent with linked records. |
| 7 | effect_on_claim | Exact bounded claim or claim-related role represented by effect on claim. Validation: non-empty when required; internally consistent with linked records. |
| 8 | alternative_explanation | Credible competing explanation that could account for the observation without accepting the preferred interpretation. Validation: non-empty when required; internally consistent with linked records. |
| 9 | repair_or_follow_up | Specific, owned and testable action for repair or follow up. Validation: non-empty when required; internally consistent with linked records. |
| 10 | status | Current lifecycle or decision status. Use the controlled vocabulary declared for the record. Controlled values: draft; candidate; reviewed; accepted locally; superseded; withdrawn. Validation: use one exact value from controlled vocabulary: lifecycle_status. |
| 11 | reviewer | Named person or competent role that inspected the current version. Validation: non-empty when required; internally consistent with linked records. |
| 12 | date | ISO 8601 date on which the action, observation or disposition occurred. Validation: ISO 8601 date (YYYY-MM-DD). |

B39. Version and Manifest Record — Full

CSV: companion/04_TEMPLATES_FULL/VERSION_MANIFEST_RECORD_FULL.csv

Purpose. Preserve provenance, supersession and derivative identity for every controlled package.

Use and completion. Complete only when the current decision requires this record. A third party can identify the source of truth, its derivatives and the status of rights, privacy and proof.

Boundary. controlled project metadata; no credentials, direct identifiers or confidential payloads Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | Object identifier | Stable ID. Validation: non-empty when required; internally consistent with linked records. |
| 2 | Authoritative filename | Exact name. Validation: non-empty when required; internally consistent with linked records. |
| 3 | Version | Explicit version. Validation: explicit version or dated revision; no ambiguous labels such as final-final. |
| 4 | Date | ISO date. Validation: ISO 8601 date (YYYY-MM-DD). |
| 5 | SHA-256 | Lowercase SHA-256 digest of the exact controlled file. Recalculate it whenever the file bytes change. Validation: non-empty when required; internally consistent with linked records. |
| 6 | Source master and hash | Upstream authority. Validation: non-empty when required; internally consistent with linked records. |
| 7 | Derived objects and hashes | Complete list. Validation: non-empty when required; internally consistent with linked records. |
| 8 | Content identity | Question, evidence, result, claim and limit preserved. Validation: non-empty when required; internally consistent with linked records. |
| 9 | Rights status | Private use, permission, licence or unresolved. Controlled values: pending clearance; cleared for declared use; restricted; prohibited; not applicable. Validation: use one exact value from controlled vocabulary: rights_status. |
| 10 | Privacy status | Public, internal, confidential, restricted or mixed. Controlled values: public; internal; confidential; restricted; mixed. Validation: use one exact value from controlled vocabulary: privacy_class. |
| 11 | Proof state | Technical, Word proof or final candidate. Controlled values: not rendered; candidate; passed technical proof; failed; pending Microsoft Word proof. Validation: use one exact value from controlled vocabulary: render_status. |
| 12 | Supersedes and superseded by | Version lineage. Validation: non-empty when required; internally consistent with linked records. |
| 13 | Manifest location | Machine-readable record. Validation: non-empty when required; internally consistent with linked records. |
| 14 | Owner, reviewer and next gate | Lifecycle record. Validation: non-empty when required; internally consistent with linked records. |

B40. Work-Unit Brief — Full

CSV: companion/04_TEMPLATES_FULL/WORK_UNIT_BRIEF_FULL.csv

Purpose. Bound one authorised unit of execution and its admission criteria.

Use and completion. Complete only when the current decision requires this record. The unit has a known starting state, expected evidence, failure rule and disposition path.

Boundary. record versions and evidence locators, not secrets, personal data or proprietary payloads Form completion does not itself establish evidence, authority or gate passage.

| No. | Field or CSV column | What to record and how to validate |
| --- | --- | --- |
| 1 | Work-unit identifier | Stable ID. Validation: non-empty when required; internally consistent with linked records. |
| 2 | Authorised commitment | Link to Design Gate record. Validation: non-empty when required; internally consistent with linked records. |
| 3 | Purpose | Decision or evidence produced. Validation: non-empty when required; internally consistent with linked records. |
| 4 | Starting state | Inputs, versions and environment. Validation: non-empty when required; internally consistent with linked records. |
| 5 | Action | Bounded execution. Validation: non-empty when required; internally consistent with linked records. |
| 6 | Expected candidate output | Object awaiting inspection. Validation: non-empty when required; internally consistent with linked records. |
| 7 | Local verification | Conformance checks. Validation: non-empty when required; internally consistent with linked records. |
| 8 | Failure evidence | What must be retained. Validation: non-empty when required; internally consistent with linked records. |
| 9 | Acceptance criterion | Condition for admission to Execution Dossier. Validation: non-empty when required; internally consistent with linked records. |
| 10 | Disposition options | Accept locally, repair, repeat, reject, defer or quarantine. Validation: non-empty when required; internally consistent with linked records. |
| 11 | Owner and reviewer | Responsibility. Validation: non-empty when required; internally consistent with linked records. |
| 12 | Date, version and status | Lifecycle record. Validation: explicit version or dated revision; no ambiguous labels such as final-final. |

Part C — Route kits

Each route kit applies the same nine gates to a different evidence obligation and inferential boundary. Use the directory files for the full gate plan and synthetic worked example.

C1. CREATE — Build-and-evaluate

Directory: companion/05_ROUTE_KITS/build_and_evaluate

| Route question | Minimum evidence | Prohibited inference |
| --- | --- | --- |
| Can a designed artefact address a bounded problem? | Requirements, rationale, accepted tests and evaluation criteria. | Local demonstration becomes production or institutional readiness |

Synthetic worked example. Traceable validation and recovery in a bounded file-submission prototype. It is a teaching object and not empirical evidence.

C2. MODEL — Algorithmic or simulation study

Directory: companion/05_ROUTE_KITS/algorithmic_simulation

| Route question | Minimum evidence | Prohibited inference |
| --- | --- | --- |
| How does a method or system behave under declared conditions? | Formal assumptions, scenarios, comparator and sensitivity analysis. | One dataset, parameter setting or machine becomes universal superiority or model truth |

Synthetic worked example. Sensitivity of API admission-control policies under bursty synthetic workloads. It is a teaching object and not empirical evidence.

C3. PREDICT — Predictive or machine-learning study

Directory: companion/05_ROUTE_KITS/predictive_machine_learning

| Route question | Minimum evidence | Prohibited inference |
| --- | --- | --- |
| How well does a model predict under a locked validation protocol? | Provenance, split logic, baseline, metrics and error analysis. | Best metric becomes universal superiority, fairness or deployment value |

Synthetic worked example. Transparent routing of service requests using a bounded text-classification baseline. It is a teaching object and not empirical evidence.

C4. MEASURE — Quantitative empirical study

Directory: companion/05_ROUTE_KITS/quantitative_empirical

| Route question | Minimum evidence | Prohibited inference |
| --- | --- | --- |
| What distribution, association or effect is supported by observed data? | Constructs, sampling, protocol, uncertainty and validity threats. | Threshold crossing becomes importance, causality or generalisability |

Synthetic worked example. Effect of a structured debugging checklist in a bounded laboratory exercise. It is a teaching object and not empirical evidence.

C5. INTERPRET — Qualitative inquiry

Directory: companion/05_ROUTE_KITS/qualitative_inquiry

| Route question | Minimum evidence | Prohibited inference |
| --- | --- | --- |
| How do participants experience or make sense of a phenomenon? | Sampling rationale, protocol, reflexive analysis and traceable interpretation. | Recurring theme becomes population prevalence or universal truth |

Synthetic worked example. How novice data analysts describe uncertainty when debugging notebook outputs. It is a teaching object and not empirical evidence.

C6. EXPLAIN IN CONTEXT — Case study

Directory: companion/05_ROUTE_KITS/case_study

| Route question | Minimum evidence | Prohibited inference |
| --- | --- | --- |
| How and why does a bounded phenomenon unfold in context? | Case boundary, multiple evidence sources and a chain of evidence. | One bounded case becomes general prevalence or universal mechanism |

Synthetic worked example. Adoption of automated dependency scanning in one university software laboratory. It is a teaching object and not empirical evidence.

C7. SYNTHESISE — Formal evidence synthesis

Directory: companion/05_ROUTE_KITS/formal_evidence_synthesis

| Route question | Minimum evidence | Prohibited inference |
| --- | --- | --- |
| What does a documented corpus support? | Protocol, reproducible search, study identity, appraisal and synthesis. | Number of favourable publications becomes consensus or universal effectiveness |

Synthetic worked example. Evidence synthesis of automated feedback for introductory programming exercises. It is a teaching object and not empirical evidence.

C8. INTEGRATE — Hybrid route

Directory: companion/05_ROUTE_KITS/hybrid_route

| Route question | Minimum evidence | Prohibited inference |
| --- | --- | --- |
| Why must two routes answer one joint question together? | Dominant logic, integration point, adequate resources and both evidence contracts. | More methods become automatic mutual validation |

Synthetic worked example. Accessibility and response performance of a campus event-notification prototype. It is a teaching object and not empirical evidence.

Part D — Digital modules DC-A–DC-E

| Module | Former book appendix | Operational content | Principal directory |
| --- | --- | --- | --- |
| DC-A | Appendix A — Quick Guide: Mandatory and Recommended | Official obligations, authorial controls and dated source status | companion/08_INSTITUTIONAL_LINKS/ |
| DC-B | Appendix B — Official Process and Calendar | Route process, current-session authority and conflict control | companion/08_INSTITUTIONAL_LINKS/ |
| DC-C | Appendix C — Documents and Evidence by Milestone | Scientific, administrative and release records by milestone | companion/08_INSTITUTIONAL_LINKS/ |
| DC-D | Appendix D — Generative AI Use, Disclosure and Responsibility | Permission, TRACE, independent verification and disclosure records | companion/06_AI_TRACE_AND_DISCLOSURE/ |
| DC-E | Appendix E — Submission and Defence Checklists | Evidence-backed submission, demonstration, presentation and defence checks | companion/07_SUBMISSION_AND_DEFENCE/ |

Book v3.9.0 contains no formal Appendices A–E. Their stable methodological principles are integrated in the book, while editable operational resources are maintained through DC-A–DC-E. The companion remains supplementary and current official sources prevail.

Release and exclusion status

• The workbook, templates, synthetic examples, schemas, registers and figure assets are licensed under CC BY 4.0.

• Scripts and code are licensed under the MIT License.

• The book manuscript, technical proof and publisher-facing files are not included.

• No Zenodo DOI is asserted in this package; consult verified release metadata for the archived version.

• Current regulations, official forms and competent written decisions prevail over dated companion records.